## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | SM/19161 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BAKSA Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.HE Dte. within Chanditala-II Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000150/2023-2024 | 1536/HUG | 24/05/2023 | 23/06/2023 | GHOSH ENTERPRISE | 11.79 | 9.45 | 80.18 | 100
2 | HOOGHLY |  | Electrical | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | SM/19161 | Augmentation | Additional quotation for Baksa w/s scheme against application no.- 5003987334 Ref ID: 860295228 |  |  | BILL/06497/2023-2024 | 13 | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.93 | 0 | 0 | 0
Total | [13 empty] | 12.72 | 9.45 | 74.33