## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solarisation of WBSEDCL energised electrical installation at different PWSS in the district of Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000642/2023-2024 | 3084/ED | 17/07/2023 | 01/01/2026 | SWITCHING AVO ELECTRO POWER LIMITED | 119.77 | 71.86 | 60 | 40
2 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Rajbalhat W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004073023 Reference Id-162187840 |  |  | BILL/02652/2024-2025 | 635 | 18/12/2024 | 18/12/2024 | WBSEDCL | 0.4 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Bhangamora W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004064057 Reference Id-502669370 |  |  | BILL/01011/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Meghsar W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004494541 Reference Id-502729411 |  |  | BILL/01018/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Saptagram W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004897016 Reference Id-102484405 |  |  | BILL/04531/2025-2026 |  | 24/11/2025 | 24/11/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Radhaballavpur W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004624721 Reference Id-102165502 |  |  | BILL/03414/2024-2025 | 702 | 17/03/2025 | 17/03/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Batanal W/S Scheme,Zone-I,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004479060 Reference Id-502846377 |  |  | BILL/02803/2024-2025 | 657 | 09/01/2025 | 09/01/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Sripur W/S Scheme,PH No-I under Electrical Division,PHE Dte. (SM/15216) Application No-5004613027 Reference Id-500980892 |  |  | BILL/04657/2025-2026 |  | 03/12/2025 | 03/12/2025 | WBSEDCL | 0.3 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Arandi W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004509610 Reference Id-102354985 |  |  | BILL/03200/2024-2025 | 707 | 17/03/2025 | 17/03/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Pownan W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004494440 Reference Id-163125848 |  |  | BILL/02822/2024-2025 | 659 | 09/01/2025 | 09/01/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Dakshin Rasulpur W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004479179 Reference Id-502300749 |  |  | BILL/02804/2024-2025 | 658 | 09/01/2025 | 09/01/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Anandapur W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004624703 Reference Id-164251389 |  |  | BILL/03416/2024-2025 | 714 | 17/03/2025 | 17/03/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Ganeshbati W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004624734 Reference Id-501523051 |  |  | BILL/03415/2024-2025 | 713 | 17/03/2025 | 17/03/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Kamarkundu W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004507779 Reference Id-167423056 |  |  | BILL/02811/2024-2025 | 656 | 09/01/2025 | 09/01/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Baidyapur W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004532019 Reference Id-502282811 |  |  | BILL/03356/2024-2025 | 715 | 17/03/2025 | 17/03/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
16 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Baruipara W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004507505 Reference Id-502128970 |  |  | BILL/01188/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. | SM/15216 | Solarisation | Solar Quotation for Bahadurpur W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004637901 Reference Id-101246038 |  |  | BILL/01143/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 0.3 | 0 | 0 | 0
Total | [13 empty] | 123.09 | 71.86 | 58.38