## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | SM/18930 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. V, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001530/2021-2022 | 174_ED | 01/02/2022 | 02/05/2022 | M/S DILIP MITRA | 6.74 | 3.37 | 50 | 50
2 | HOOGHLY |  | Electrical | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | SM/18930 | Augmentation | Quotation Bill for New Service Connection at Bandipur W/S. Sch |  |  | BILL/06036/2023-2024 | 738 | 07/02/2024 |  | WBSEDCL | 18.99 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | SM/18930 | Augmentation | Quotation Bill for New Service Connection at Bandipur W/S. Sch |  |  | BILL/06036/2023-2024 | 738 | 07/02/2024 |  | WBSEDCL | 18.99 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | SM/18930 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. VI, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/002574/2022-2023 | 3483/ED | 30/12/2022 | 30/03/2023 | M/S S.R. ENTERPRISE | 10.82 | 5.4 | 49.89 | 30
Total | [13 empty] | 55.55 | 8.77 | 15.79