## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | SM/18931 | Augmentation | Supply delivery and installation of Chlorinator for Baruipara w/s scheme PH No. VII District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001528/2021-2022 | 83/HMSD | 14/01/2022 | 13/02/2022 | M/S CHANDIMATA ELECTRICALS | 0.76 | 0 | 0 | 100
2 | HOOGHLY |  | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VI, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001522/2021-2022 | 171/ED | 01/02/2022 | 02/05/2022 | ESENCE ENGINEERING CONCERN | 6.58 | 0 | 0 | 100
3 | HOOGHLY |  | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VII, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001521/2021-2022 | 172/ED | 01/02/2022 | 02/05/2022 | RAJIB COMPANY | 6.59 | 0 | 0 | 100
4 | HOOGHLY |  | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | SM/18931 | Augmentation | Supply delivery and installation of Chlorinator for BARUIPARA w/s scheme PH No. VI District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001523/2021-2022 | 103/HMSD | 18/01/2022 | 25/01/2022 | STANDARD ELECTRICALS | 0.76 | 0 | 0 | 100
5 | HOOGHLY |  | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. V, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001533/2021-2022 | 170/ED | 01/02/2022 | 02/05/2022 | BIJAN ENTERPRISE | 6.63 | 0 | 0 | 100
6 | HOOGHLY |  | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No.- IV, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001280/2023-2024 | 2442_ED | 13/10/2023 | 27/11/2023 | R.N.S. TRADING | 6.14 | 0 | 0 | 50
Total | [13 empty] | 27.46 | 0 | 0