## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 21/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 156.83 | 29.23 | 50
2 | HOWRAH |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 21/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 156.83 | 29.23 | 50
3 | NORTH 24 PARAGANAS |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 21/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 156.83 | 29.23 | 50
4 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 21/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 156.83 | 29.23 | 50
Total | [13 empty] | 2146.45 | 627.33 | 29.23