## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 27/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 314.01 | 58.52 | 75
2 | HOWRAH |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 27/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 314.01 | 58.52 | 75
3 | NORTH 24 PARGANAS |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 27/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 314.01 | 58.52 | 75
4 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 27/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 314.01 | 58.52 | 75
5 | HOOGHLY |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 2684/RS | 29/08/2023 | 27/02/2024 | LIMRA SOCIAL WELFARE SOCIETY | 215.95 | 215.95 | 100 | 99
6 | HOWRAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 2684/RS | 29/08/2023 | 27/02/2024 | LIMRA SOCIAL WELFARE SOCIETY | 215.95 | 215.95 | 100 | 99
7 | NORTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 2684/RS | 29/08/2023 | 27/02/2024 | LIMRA SOCIAL WELFARE SOCIETY | 215.95 | 215.95 | 100 | 99
8 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 2684/RS | 29/08/2023 | 27/02/2024 | LIMRA SOCIAL WELFARE SOCIETY | 215.95 | 215.95 | 100 | 99
9 | HOOGHLY |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2702/RS | 31/08/2023 | 29/02/2024 | IMAGIN | 259.77 | 259.77 | 100 | 35
10 | HOWRAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2702/RS | 31/08/2023 | 29/02/2024 | IMAGIN | 259.77 | 259.77 | 100 | 35
11 | NORTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2702/RS | 31/08/2023 | 29/02/2024 | IMAGIN | 259.77 | 259.77 | 100 | 35
12 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2702/RS | 31/08/2023 | 29/02/2024 | IMAGIN | 259.77 | 259.77 | 100 | 35
13 | HOOGHLY |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 3110/RS | 10/10/2023 | 09/10/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 169.73 | 169.73 | 100 | 50
14 | HOWRAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 3110/RS | 10/10/2023 | 09/10/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 169.73 | 169.73 | 100 | 50
15 | NORTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 3110/RS | 10/10/2023 | 09/10/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 169.73 | 169.73 | 100 | 50
16 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purba Midnapore, Howrah, Hooghly and North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19001 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 3110/RS | 10/10/2023 | 09/10/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 169.73 | 169.73 | 100 | 50
Total | [13 empty] | 4728.27 | 3837.87 | 81.17