## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | Assistant Engineer | Junior Engineer | ORD/000363/2023-2024 | 829/RS | 13/03/2024 | 05/11/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 118.92 | 0 | 0 | 50
2 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | Assistant Engineer | Junior Engineer | ORD/000363/2023-2024 | 829/RS | 13/03/2024 | 05/11/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 118.92 | 0 | 0 | 50
3 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | Assistant Engineer | Junior Engineer | ORD/000363/2023-2024 | 829/RS | 13/03/2024 | 05/11/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 118.92 | 0 | 0 | 50
4 | HOOGHLY |  | RCFA Division -I | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Acceptance cum Work Order for Engagement of Implementation Support Agency (ISAs) under JJM/Jal Swapna in the District of Paschim Bardhaman. (w.e.f. 12.09.2024 to 10.03.2025) | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer 10,Junior Engineer 6 | ORD/000080/2024-2025 | 2034/RCD-I | 21/08/2024 | 26/03/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 92.17 | 0 | 0 | 50
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Acceptance cum Work Order for Engagement of Implementation Support Agency (ISAs) under JJM/Jal Swapna in the District of Paschim Bardhaman. (w.e.f. 12.09.2024 to 10.03.2025) | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer 10,Junior Engineer 6 | ORD/000080/2024-2025 | 2034/RCD-I | 21/08/2024 | 26/03/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 92.17 | 0 | 0 | 50
6 | PASCHIM MEDINIPUR |  | RCFA Division -I | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Acceptance cum Work Order for Engagement of Implementation Support Agency (ISAs) under JJM/Jal Swapna in the District of Paschim Bardhaman. (w.e.f. 12.09.2024 to 10.03.2025) | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer 10,Junior Engineer 6 | ORD/000080/2024-2025 | 2034/RCD-I | 21/08/2024 | 26/03/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 92.17 | 0 | 0 | 50
7 | HOOGHLY |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000208/2024-2025 | 3198/RS | 31/12/2024 | 31/03/2025 | LIMRA SOCIAL WELFARE SOCIETY | 109.46 | 0 | 0 | 99
8 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000208/2024-2025 | 3198/RS | 31/12/2024 | 31/03/2025 | LIMRA SOCIAL WELFARE SOCIETY | 109.46 | 0 | 0 | 99
9 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000208/2024-2025 | 3198/RS | 31/12/2024 | 31/03/2025 | LIMRA SOCIAL WELFARE SOCIETY | 109.46 | 0 | 0 | 99
10 | HOOGHLY |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 733/RS | 04/03/2024 | 04/01/2025 | LIMRA SOCIAL WELFARE SOCIETY | 329.67 | 0 | 0 | 50
11 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 733/RS | 04/03/2024 | 04/01/2025 | LIMRA SOCIAL WELFARE SOCIETY | 329.67 | 0 | 0 | 50
12 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Paschim Medinipur, Hooghly and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19236 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 733/RS | 04/03/2024 | 04/01/2025 | LIMRA SOCIAL WELFARE SOCIETY | 329.67 | 0 | 0 | 50
Total | [13 empty] | 1950.67 | 0 | 0