## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & Capacity building activities at Paschim Medinipur and Hooghly districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19357 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 598/RS | 13/03/2025 | 13/03/2026 | LIMRA SOCIAL WELFARE SOCIETY | 327.93 | 0 | 0 | 25
2 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & Capacity building activities at Paschim Medinipur and Hooghly districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19357 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Hooghly District. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 598/RS | 13/03/2025 | 13/03/2026 | LIMRA SOCIAL WELFARE SOCIETY | 327.93 | 0 | 0 | 25
3 | HOOGHLY |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & Capacity building activities at Paschim Medinipur and Hooghly districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19357 |  | Engagement of Implementation Support Agency (ISA) for Implementation of commudity mobilization & capacity building activities related to House Hold tap connection (FHTC) in Paschim Midnapur district Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 587/RS | 13/03/2025 | 13/03/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 424.43 | 0 | 0 | 25
4 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & Capacity building activities at Paschim Medinipur and Hooghly districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19357 |  | Engagement of Implementation Support Agency (ISA) for Implementation of commudity mobilization & capacity building activities related to House Hold tap connection (FHTC) in Paschim Midnapur district Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 587/RS | 13/03/2025 | 13/03/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 424.43 | 0 | 0 | 25
Total | [13 empty] | 1504.72 | 0 | 0