## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR and Bid documents for new Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under under Chinsurah Sub Division, Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000033/2022-2023 | 793/Hug | 18/04/2022 | 02/07/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 125.19 | 113.17 | 90.4 | 0
2 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of MALAYPUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | Assistant Engineer |  | ORD/000384/2021-2022 | 615/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.29 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Dihibatpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Dihibatpur Part-A) | Assistant Engineer | Junior Engineer (Civill) | ORD/000069/2022-2023 | 340/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 4.62 | 98.71 | 0
4 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Shyampur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Shyampur Part-A) | Assistant Engineer | Junior Engineer (Civill) | ORD/000071/2022-2023 | 342/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.73 | 4.72 | 99.79 | 0
5 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Additional survey work for preparation of DPR for Augmentation of Shyampur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Shyampur Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000072/2022-2023 | 343/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.3 | 1.25 | 95.69 | 0
6 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Additional survey work for preparation of DPR for Augmentation of Dihibatpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Dihibatpur Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000070/2022-2023 | 341/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.46 | 0.46 | 98.27 | 0
7 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Additional survey work for preparation of DPR for Augmentation of Krishnanagar Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Krishnanagar Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000102/2022-2023 | 392/Arg | 31/05/2022 | 30/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.34 | 0.34 | 99.73 | 0
8 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Khanakul Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000103/2022-2023 | 393/Arg | 31/05/2022 | 30/06/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.74 | 4.68 | 98.76 | 0
9 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Gobindapur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000104/2022-2023 | 394/Arg | 31/05/2022 | 30/06/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.3 | 3.25 | 98.49 | 0
10 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Balipur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Balipur Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000106/2022-2023 | 406/Arg | 07/06/2022 | 07/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.02 | 1.96 | 97.38 | 0
11 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Krishnanagar Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Krishnanagar Part-A). | Assistant Engineer | Junior Engineer (Civill) | ORD/000101/2022-2023 | 391/Arg | 31/05/2022 | 30/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 4.64 | 99.15 | 0
12 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Rambati PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000570/2022-2023 | 664/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 2.51 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Paschim Narayanpur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000575/2022-2023 | 670/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 7.18 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Srirampur Piped Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. Part-A | Assistant Engineer | Junior Engineer (Civill) | ORD/000399/2022-2023 | 623/Arg | 01/09/2022 | 01/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.42 | 4.35 | 98.41 | 0
15 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Atisara PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000578/2022-2023 | 673/Chan | 13/12/2022 | 28/12/2022 | M/S R. DUTTA & CO. | 8.52 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Additional survey work for Preparation of DPR for Augmentation of Srirampur Piped Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. Part-B | Assistant Engineer | Junior Engineer (Civill) | ORD/000400/2022-2023 | 625/Arg | 01/09/2022 | 01/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.13 | 1.12 | 99.01 | 0
17 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Nanda PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000896/2022-2023 | 0666/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 7.34 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Basubati PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000897/2022-2023 | 0668/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 7.3 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Paschim Narayanpur PWSS under Chandannagar Sub - Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000931/2022-2023 | 670/1/Hug | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 7.2 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, design, drawing & DPR Preparation of Nawpara PWSS under Chandannagar Sub-Division, of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000934/2022-2023 | 2177/HUG | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 7 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Bahirkhanda PWSS under Chandannagar Sub - Division, PHE Dte | Assistant Engineer (Civil) |  | ORD/000933/2022-2023 | 672/1/hug | 13/12/2022 | 28/12/2022 | M/S R. DUTTA & CO. | 10.43 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Balipur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Balipur Part-A) | Assistant Engineer | Junior Engineer (Civill) | ORD/000105/2022-2023 | 395/Arg | 31/05/2022 | 30/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.58 | 4.56 | 99.68 | 0
23 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR and Bid documents for new Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under Arambag Sub Division, Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000032/2022-2023 | 792/Hug | 18/04/2022 | 17/07/2022 | RADIANT | 227.1 | 227.08 | 99.99 | 0
24 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR and Bid documents for new Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under under Serampore Sub Division, Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000031/2022-2023 | 791/Hug | 18/04/2022 | 02/07/2022 | THE NISARGA CONSULTANCY | 120.96 | 114.99 | 95.06 | 0
25 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bainchipota (Zone-II) PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000501/2022-2023 | 618/Chan | 02/12/2022 | 17/12/2022 | TECHVISION | 2.57 | 2.57 | 100 | 0
26 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bighati(Zone-II) PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000504/2022-2023 | 621/Chan | 02/12/2022 | 17/12/2022 | TECHVISION | 4.48 | 4.48 | 100 | 0
27 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bahirkhanda PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000577/2022-2023 | 672/Chan | 13/12/2022 | 28/12/2022 | M/S R. DUTTA & CO. | 10.42 | 10.42 | 100 | 100
28 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bainchipota (Zone -I)PWSS under Chandannagar Sub - Division, PHE Dte | Assistant Engineer (Civil) |  | ORD/000502/2022-2023 | 619/Chan | 02/12/2022 | 17/12/2022 | TECHVISION | 4.7 | 4.7 | 100 | 0
29 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bighati(Zone -I) PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000503/2022-2023 | 620/Chan | 02/12/2022 | 17/12/2022 | TECHVISION | 5.01 | 5.01 | 100 | 0
30 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Nawpara PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000413/2022-2023 | 515/Chan | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 6.83 | 6.83 | 100 | 100
31 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bhagabatipur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000723/2022-2023 | 97/Chan | 27/02/2023 | 14/03/2023 | APEX ENGINEERING | 0.63 | 0.63 | 100 | 0
32 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Parjana PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000725/2022-2023 | 98/Chan | 27/02/2023 | 14/03/2023 | APEX ENGINEERING | 5.99 | 5.99 | 100 | 0
33 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Sirazpur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000728/2022-2023 | 101/Chan | 27/02/2023 | 14/03/2023 | APEX ENGINEERING | 5.11 | 5.11 | 100 | 0
34 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Aima Chapsara PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000726/2022-2023 | 99/Hug | 27/02/2023 | 14/03/2023 | APEX ENGINEERING | 4.38 | 4.38 | 100 | 0
35 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Purushottampur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000727/2022-2023 | 100/Hug | 27/02/2023 | 14/03/2023 | APEX ENGINEERING | 4.29 | 4.29 | 100 | 0
36 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of ATISARA PWSS under Chandannagar Sub - Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000928/2022-2023 | 673/1/Hug | 13/12/2022 | 28/12/2022 | M/S R. DUTTA & CO. | 9.62 | 8.52 | 88.56 | 100
37 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Basubati PWSS under Chandannagar Sub - Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000929/2022-2023 | 668/1/Hug | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 8.25 | 7.3 | 88.52 | 100
38 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Nasibpur PWSS under Chandannagar Sub - Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000930/2022-2023 | 667/1/Hug | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 7.51 | 7.18 | 95.64 | 100
39 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Rambati PWSS under Chandannagar Sub - Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000932/2022-2023 | 664/1/Hug | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 2.52 | 2.51 | 99.64 | 100
40 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of 1 No. DPR for New Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under CHANDANNAGAR Sub Division, Hooghly Division, PHE Dte. under JJM. (Annexure-I) | Assistant Engineer (Civil) |  | ORD/000533/2023-2024 | 3063/HUG | 11/10/2023 | 25/11/2023 | HORIZEN | 9.65 | 9.65 | 100 | 98
41 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Nasibpur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000574/2022-2023 | 669/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 5.59 | 0 | 0 | 0
42 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route survey Design drawing & DPR preparation of Kamarkundu Zone- VI & VII PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer(HQ) |  | ORD/000175/2022-2023 | 269/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.3 | 4.26 | 99.14 | 95
43 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Nanda PWSS under Chandannagar Sub - Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000926/2022-2023 | 666/1/Hug | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 8.29 | 7.34 | 88.49 | 100
44 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route survey Design drawing & DPR preparation of Kamarkundu Zone- IV & V PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer(HQ) |  | ORD/000174/2022-2023 | 268/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.74 | 4.7 | 99.08 | 95
45 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-A). | Assistant Engineer (Civil) |  | ORD/000712/2023-2024 | 1002/Chan | 21/12/2023 | 05/01/2024 | TECHVISION | 0.84 | 0.84 | 100 | 98
46 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-II) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-C). | Assistant Engineer (Civil) |  | ORD/000711/2023-2024 | 1001/Chan | 21/12/2023 | 05/01/2024 | TECHVISION | 0.78 | 0.78 | 100 | 98
47 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-II) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-B) | Assistant Engineer (Civil) |  | ORD/000710/2023-2024 | 1000/Chan | 21/12/2023 | 05/01/2024 | TECHVISION | 0.98 | 0.98 | 100 | 98
48 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-B) | Assistant Engineer (Civil) |  | ORD/000713/2023-2024 | 1003/Chan | 21/12/2023 | 05/01/2024 | TECHVISION | 0.73 | 0.73 | 100 | 98
49 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-C) | Assistant Engineer (Civil) |  | ORD/000714/2023-2024 | 1004/Chan | 21/12/2023 | 05/01/2024 | TECHVISION | 0.37 | 0.37 | 100 | 98
50 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-II) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-A) | Assistant Engineer (Civil) |  | ORD/000709/2023-2024 | 999/Chan | 21/12/2023 | 05/01/2024 | TECHVISION | 0.84 | 0 | 0 | 98
51 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-D). | Assistant Engineer (Civil) |  | ORD/000715/2023-2024 | 1005/Chan | 21/12/2023 | 05/01/2024 | TECHVISION | 0.78 | 0.78 | 100 | 98
52 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kapasharia (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001454/2023-2024 | 127/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
53 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gopalpur(Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001462/2023-2024 | 135/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
54 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection(FHTC) of Rajballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub - Division PHE Dte. (Part- C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000127/2024-2025 | 748/Chan | 29/08/2024 | 13/09/2024 | TECHVISION | 0.78 | 0.78 | 100 | 100
55 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Jagmohanpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001450/2023-2024 | 121/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
56 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Krishna Ballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000116/2024-2025 | 745/Chan | 29/08/2024 | 13/09/2024 | ENVIROTECH SOLUTIONS | 0.95 | 0.95 | 100 | 100
57 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection(FHTC) of Rajballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub - Division PHE Dte. (Part- B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000126/2024-2025 | 747/Chan | 29/08/2024 | 13/09/2024 | TECHVISION | 0.84 | 0.84 | 100 | 100
58 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Mundalika (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001458/2023-2024 | 131/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
59 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Mundalika (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001459/2023-2024 | 132/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
60 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Pairagacha (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001471/2023-2024 | 137/SER | 23/02/2024 | 09/03/2024 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
61 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Bandhpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001466/2023-2024 | 122/SER | 23/02/2024 | 09/03/2024 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
62 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Bhagabatipur (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001467/2023-2024 | 123/SER | 23/02/2024 | 09/03/2024 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
63 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Nababpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001469/2023-2024 | 125/SER | 23/02/2024 | 09/03/2024 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
64 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providng Functional Household Tap Connection (FHTC) of Krishna BALLABHBATI Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, P.H.E Dte. (PART-A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000105/2024-2025 | 744/Chan | 29/08/2024 | 13/09/2024 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
65 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kumirmora (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001448/2023-2024 | 119/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
66 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Krishna Ballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000118/2024-2025 | 746/Chan | 29/08/2024 | 13/09/2024 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
67 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Bhagabatipur (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001468/2023-2024 | 124/SER | 23/02/2024 | 09/03/2024 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
68 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Pairagacha (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001470/2023-2024 | 136/SER | 23/02/2024 | 09/03/2024 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
69 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kapasharia (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001453/2023-2024 | 126/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
70 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kotalpur (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001456/2023-2024 | 129/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
71 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kotalpur (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001457/2023-2024 | 130/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
72 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Jagannathpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001460/2023-2024 | 133/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
73 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gopalpur(Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001461/2023-2024 | 134/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
74 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kumirmora (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001447/2023-2024 | 118/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
75 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Haripur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001449/2023-2024 | 120/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
76 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Dudhkalmi Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001455/2023-2024 | 128/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
77 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Binagram PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000572/2022-2023 | 667/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 7.5 | 0 | 0 | 100
78 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Nasibpur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000898/2022-2023 | 0669/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 5.9 | 0 | 0 | 100
79 | HOOGHLY |  | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. | SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Diara PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000899/2022-2023 | 0671/Chan | 13/12/2022 | 28/12/2022 | INDRANIL DUTTA & ASSOCIATES | 5.01 | 0 | 0 | 100
Total | [13 empty] | 731.06 | 622.57 | 85.16