## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 258.07 | 35.94 | 57
2 | HOWRAH |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 258.07 | 35.94 | 57
3 | PASCHIM MEDINIPUR |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 258.07 | 35.94 | 57
4 | PURBA MEDINIPUR |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 258.07 | 35.94 | 57
5 | HOOGHLY |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under JJM in the State of West Bengal For 3(Three) Zone covering 6(Six) districts like Puraba Midnapore, Paschim Midnapore, Coochbehar, Alipurduar, Jalpaiguri, Uttar Dinajpur and Kalimpong against Zone VIII, ZONE III & Zone II repectively. |  |  | ORD/000131/2024-2025 | 2594/RS | 27/09/2024 | 27/11/2024 | TUV SUD SOUTH ASIA PVT. LTD. | 158.99 | 10.41 | 6.55 | 5
6 | HOWRAH |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under JJM in the State of West Bengal For 3(Three) Zone covering 6(Six) districts like Puraba Midnapore, Paschim Midnapore, Coochbehar, Alipurduar, Jalpaiguri, Uttar Dinajpur and Kalimpong against Zone VIII, ZONE III & Zone II repectively. |  |  | ORD/000131/2024-2025 | 2594/RS | 27/09/2024 | 27/11/2024 | TUV SUD SOUTH ASIA PVT. LTD. | 158.99 | 10.41 | 6.55 | 5
7 | PASCHIM MEDINIPUR |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under JJM in the State of West Bengal For 3(Three) Zone covering 6(Six) districts like Puraba Midnapore, Paschim Midnapore, Coochbehar, Alipurduar, Jalpaiguri, Uttar Dinajpur and Kalimpong against Zone VIII, ZONE III & Zone II repectively. |  |  | ORD/000131/2024-2025 | 2594/RS | 27/09/2024 | 27/11/2024 | TUV SUD SOUTH ASIA PVT. LTD. | 158.99 | 10.41 | 6.55 | 5
8 | PURBA MEDINIPUR |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Howrah, Hooghly, Purba Medinipur & Paschim Medinipur District of West Bengal. | SM/10540 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under JJM in the State of West Bengal For 3(Three) Zone covering 6(Six) districts like Puraba Midnapore, Paschim Midnapore, Coochbehar, Alipurduar, Jalpaiguri, Uttar Dinajpur and Kalimpong against Zone VIII, ZONE III & Zone II repectively. |  |  | ORD/000131/2024-2025 | 2594/RS | 27/09/2024 | 27/11/2024 | TUV SUD SOUTH ASIA PVT. LTD. | 158.99 | 10.41 | 6.55 | 5
Total | [13 empty] | 3508.18 | 1073.91 | 30.61