## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 4463/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 407.26 | 304.22 | 74.7 | 83
2 | JHARGRAM |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 4463/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 407.26 | 304.22 | 74.7 | 83
3 | NADIA |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 4463/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 407.26 | 304.22 | 74.7 | 83
4 | NORTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 4463/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 407.26 | 304.22 | 74.7 | 83
5 | PASCHIM MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 4463/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 407.26 | 304.22 | 74.7 | 83
6 | PURBA MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 4463/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 407.26 | 304.22 | 74.7 | 83
7 | SOUTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 4463/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 407.26 | 304.22 | 74.7 | 83
8 | BANKURA |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 4464/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 859.46 | 276.19 | 32.14 | 81
9 | JHARGRAM |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 4464/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 859.46 | 276.19 | 32.14 | 81
10 | NADIA |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 4464/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 859.46 | 276.19 | 32.14 | 81
11 | NORTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 4464/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 859.46 | 276.19 | 32.14 | 81
12 | PASCHIM MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 4464/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 859.46 | 276.19 | 32.14 | 81
13 | PURBA MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 4464/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 859.46 | 276.19 | 32.14 | 81
14 | SOUTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at South 24 Parganas, North 24 Parganas, Nadia, Purba Medinipur, Paschim Medinipur, Jhargram and Bankura districts under Jal Jeevan Mission (JJM). | SM/11207 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 4464/RS | 02/08/2022 | 29/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 859.46 | 276.19 | 32.14 | 81
Total | [13 empty] | 8867.08 | 4062.9 | 45.82