## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06792 | Retrofitting | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Ramchandrapur (5) & Nutangar (34) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. ( MB No - 3947) |  |  | VCH/001532/2020-2021 | FHTC/260 | 04/02/2021 | 04/02/2021 | M/S TARUN KUMAR PATRA | 19.64 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06792 | Retrofitting | Work Order for Household survey in Ramchandrapur (5), Nutangar (34) & Junbakra (35) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 36) |  | Junior Engineer | ORD/000539/2020-2021 | 278/KSD | 10/12/2020 | 10/02/2021 | M/S TARUN KUMAR PATRA | 0.31 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06792 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Junbakra (35) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000300/2020-2021 | 1423/BQA | 09/10/2020 | 08/11/2020 | APEX ENTERPRISE | 34.84 | 3.38 | 9.71 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06792 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Ramchandrapur (5) & Nutangar (34) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000299/2020-2021 | 1422/BQA | 09/10/2020 | 08/11/2020 | M/S TARUN KUMAR PATRA | 31.87 | 1.84 | 5.77 | 20
Total | [13 empty] | 86.66 | 5.22 | 6.02