## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Lakshmisagar (43) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - C) ( MB No - 3946) |  |  | VCH/001530/2020-2021 | FHTC/260 | 04/02/2021 | 04/02/2021 | M/S TARUN KUMAR PATRA | 22.8 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Panchal (Zone - ll) under Bishnupur Sub - Division of Bankura Division, PHE Dte. part -B block - Sonamukhi , ..Total House Hold -69 ( MB No - 3313)" |  |  | VCH/001436/2020-2021 | FHTC/284 | 03/03/2021 | 03/03/2021 | BIJOY KOLEY | 4.6 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Lakshmisagar (43) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - A) ( MB No - 3945) |  |  | VCH/001533/2020-2021 | FHTC/260 | 04/02/2021 | 04/02/2021 | M/S TARUN KUMAR PATRA | 21.68 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  |  | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 03/03/2021 | EARTHMOVING (INDIA) | 27.48 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kumarpur (209), Bansi (225), Nimdangra (226), Chhota Salbani (227), Barasalbani (228), Amdani (229), Jetpara (280) & Dharampur (281) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3954) |  |  | VCH/001553/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | MUNMUN UPADHYAY | 24.45 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Work Order for Household survey in Lakshmisagar (43) mouza to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 35) |  | Junior Engineer | ORD/000538/2020-2021 | 277/KSD | 10/12/2020 | 10/02/2021 | M/S TARUN KUMAR PATRA | 0.47 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000296/2020-2021 | 1419/BQA | 09/10/2020 | 08/11/2020 | M/S TARUN KUMAR PATRA | 36.53 | 0 | 0 | 20
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) |  | Junior Engineer | ORD/000297/2020-2021 | 1420/BQA | 09/10/2020 | 08/11/2020 | M/S TARUN KUMAR PATRA | 28.21 | 0 | 0 | 20
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) |  | Junior Engineer | ORD/000298/2020-2021 | 1421/BQA | 09/10/2020 | 08/11/2020 | M/S TARUN KUMAR PATRA | 30.11 | 0 | 0 | 20
Total | [13 empty] | 196.33 | 0 | 0