## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r | SM/06797 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000293/2020-2021 | 1416/BQA | 09/10/2020 | 08/11/2020 | EARTHMOVING (INDIA) | 37.66 | 0 | 0 | 20
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r | SM/06797 | Retrofitting | Work Order for Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nehilya (277) & Gopalpur (301) mouzas under Dhanara G.P. for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/001096/2021-2022 | 459\KSD | 11/05/2021 | 21/05/2021 | SIBSANKAR CHOWDHURY | 0 | 0 | NAN | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r | SM/06797 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nehilya (277) & Gopalpur (301) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000378/2020-2021 | 1778/BQA | 09/12/2020 | 08/01/2021 | SIB SANKAR CHOWDHURY | 33.24 | 0 | 0 | 90
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r | SM/06797 | Retrofitting | Work Order for Household survey in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nehilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) & Salbani (342) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 34) |  | Junior Engineer | ORD/000537/2020-2021 | 276/KSD | 10/12/2020 | 10/02/2021 | SIB SANKAR CHOWDHURY | 0.27 | 0 | 0 | 90
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r | SM/06797 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Raghunathpur (303) & Salbani (342) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000379/2020-2021 | 1779/BQA | 09/12/2020 | 08/01/2021 | SIB SANKAR CHOWDHURY | 20.21 | 0 | 0 | 90
Total | [13 empty] | 91.39 | 0 | 0