## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kotalsol (108), Chiltore (109) & Jhola (110) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2020-2021 | 1413/BQA | 09/10/2020 | 08/11/2020 | GOPAL CHANDRA CHOUDHURY | 36.79 | 2.5 | 6.8 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000291/2020-2021 | 1414/BQA | 09/10/2020 | 08/11/2020 | GOPAL CHANDRA CHOUDHURY | 34.86 | 0.69 | 1.98 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dhabani (195), Chhota Amjhor (196), Kuchlaghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200) & Danrkini (208) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3955) |  |  | VCH/001552/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | SUMITA UPADHYAY | 20.58 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  |  | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 03/03/2021 | EARTHMOVING (INDIA) | 27.48 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Lakshmisagar (43) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - B) ( MB No - 3944) |  |  | VCH/001529/2020-2021 | FHTC/260 | 04/02/2021 | 04/02/2021 | M/S TARUN KUMAR PATRA | 22.67 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10), |  |  | VCH/001546/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | PRADYUMNA KOLEY | 3.1 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Laying extra UPVC pipe line to cover Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) , Dharmapur (133) Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura Under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/001096/2021-2022 |  | 21/09/2021 | 21/09/2021 | GOPAL CHANDRA CHOUDHURY | 3.98 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001545/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | PRADYUMNA KOLEY | 2.81 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Work Order for Household survey in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 30) |  | Junior Engineer | ORD/000533/2020-2021 | 272/KSD | 10/12/2020 | 10/02/2021 | SUBHADIP KOLEY | 0.3 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | SM/06799 | Retrofitting | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 26/08/2022 | SUMITA UPADHYAY | 13.03 | 0.97 | 7.41 | 0
Total | [13 empty] | 165.6 | 4.16 | 2.51