## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas | SM/06801 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000352/2020-2021 | 1777/BQA | 09/12/2020 | 08/01/2021 | GOPAL CHANDRA CHOUDHURY | 36.98 | 1.64 | 4.43 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas | SM/06801 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001415/2020-2021 |  | 01/03/2021 | 01/03/2021 | GOPAL CHANDRA CHOUDHURY | 35.29 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas | SM/06801 | Retrofitting | Work Order for Household survey in Katgara (134), Basudebpur (135), Bagjanta (136) & Sidi (137) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 31) |  | Junior Engineer | ORD/000534/2020-2021 | 273/KSD | 10/12/2020 | 10/02/2021 | GOPAL CHANDRA CHOWDHURY | 0.18 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas | SM/06801 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 125 |  | Junior Engineer | ORD/000008/2020-2021 | 609/BQA | 10/02/2021 | 12/03/2021 | OSMAN SEKH | 8.39 | 10.06 | 119.81 | 0
Total | [13 empty] | 80.84 | 11.7 | 14.47