## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 (Akurbad & Banki, ) Total House Hold - 633" |  | Junior Engineer | ORD/000318/2020-2021 | 1368/BQA | 08/10/2020 | 07/11/2020 | GOPAL CHANDRA CHOUDHURY | 43.68 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576" |  | Junior Engineer | ORD/000317/2020-2021 | 1367/BQA | 08/10/2020 | 07/11/2020 | GOPAL CHANDRA CHOUDHURY | 43.69 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Engagement of 1 (one) no qualified computer operator (Category-A) for office of the Superinteding Engineer, PIU Bankura, WBDWSIP P.H.E. Dte. (w.e.f 01.08.20 to 31.07.21 ( 12 months) (Dec 20 & Jan - 2021) |  |  | VCH/001565/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 23/02/2021 | M/S BHATTACHARJEE & CO , | 0.36 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | " Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-D) , Total House Hold - 154 . ( MB No - 3775)" |  |  | VCH/001550/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | TAPAS DEY | 10.63 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhabpur (252) , Labdapara (265) & Birkham (266) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3952) |  |  | VCH/001551/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | UTTAM KUMAR SINHAMAHAPATRA | 3.7 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - B ( MB No - 3951) |  |  | VCH/001555/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | UTTAM KUMAR SINHAMAHAPATRA | 3.34 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Laying extra UPVC pipeline to Cover Pratappur , Balarampur, Telegarah, Chapatara & Sendra Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/000848/2021-2022 |  | 01/09/2021 | 01/09/2021 | GOPAL CHANDRA CHOUDHURY | 4.59 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Engagement of one(1) no qualified computer operator ( Category-A) in computer application (one year) for office of the Assistant Engineer, RWS Bankura Sub - Division PHE Dte. (01.08.20 to 31.07.21 ( 12 months) |  |  | VCH/001566/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 23/02/2021 | BANASRI KUNDU | 0.73 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A ( MB No - 3951) |  |  | VCH/001554/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | UTTAM KUMAR SINHAMAHAPATRA | 3.18 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Engagement of 1 (one) no qualified computer operator (Category-A) for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. (w.e.f 01.08.20 to 31.07.21 ( 12 months) (Jan - 2021) |  |  | VCH/001567/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 23/02/2021 | RAJU DUTTA | 0.18 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576" |  |  | VCH/001390/2020-2021 |  | 01/03/2021 | 01/03/2021 | GOPAL CHANDRA CHOUDHURY | 28.72 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Engagement of Computer Operator (Category - A) for office work of the Assistant Engineer, Bankura Sadar Sub - Division PHE Dte. of 01.08.20 to 31.07.21 ( 12 months) (Dec 20 & Jan - 2021) |  |  | VCH/001564/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 23/02/2021 | ABHIJIT MALAKAR | 0.34 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 ( MB No - 3993)" |  |  | VCH/001423/2020-2021 |  | 01/03/2021 | 01/03/2021 | GOPAL CHANDRA CHOUDHURY | 38.44 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Survey work for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 06 nos, (Akurbad, Banki, Matranga, Pratappur, Balarampur & Teleghra.) Total House Hold - 1209. |  |  | VCH/001345/2021-2022 |  | 28/09/2021 | 28/09/2021 | TAPAS DEY | 0.33 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Bangaria & Hirakon mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001918/2020-2021 | FHTC/294 | 01/03/2021 | 01/03/2021 | UTTAM KUMAR SINHAMAHAPATRA | 4.31 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kapila (270) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part -A ( MB No - 3952) |  |  | VCH/001556/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | UTTAM KUMAR SINHAMAHAPATRA | 2.51 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | " Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 04 (Kurulia ,Majdangra , Gadardihi Balarampur, & Gobindapur(PART-B) ), Total House Hold - 155 . ( MB No - 3775)" |  |  | VCH/001549/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | AJIT KUMAR PAUL | 10.59 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kapila (270) mouzas by retrofitting zone - E of Khatra -Hirbandh-Ranibandh Water Supply Scheme for (BRGF PH - l ) at block Hirbandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part -B ( MB No - 3952) |  |  | VCH/001557/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | UTTAM KUMAR SINHAMAHAPATRA | 2.72 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Engagement of one(1) no qualified computer operator ( Category-C) in computer application for Account Section of office of the Executive Engineer, Bankura Division PHE Dte. ( 01/03/20 to 28/02/21) (Jan - 2021) |  |  | VCH/001569/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 23/02/2021 | SIMA GORAI | 0.14 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Engagement of 1 (one) no qualified computer operator (Category-A) for office of the Executive Engineer, Bankura Division, P.H.E. Dte.. (w.e.f 01.08.20 to 31.07.21 ( 12 months) (Jan - 2021) |  |  | VCH/001568/2020-2021 | FHTC/COM/OP/285 | 23/02/2021 | 23/02/2021 | RAJESH SHARMA | 0.18 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( MB No - 3856) |  |  | VCH/001430/2020-2021 | FHTC/284 | 03/03/2021 | 03/03/2021 | EARTHMOVING (INDIA) | 27.48 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Laying HDPE Pipe Line to increase pressure at teleghra'banki,narrah karmakarpara,sayanipara, adra,paschim ratanpur & sibrampur tantipara for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) & CHERABASTA (ZONE-K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000477/2022-2023 | 609/BSD | 16/08/2022 | 06/09/2022 | COSMIC CONSTRUCTION | 4.99 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | SM/06802 | Retrofitting | Road restoration works at Khyarkanali, Belboni, Cherabasta, Uparbandh, Sirsara, Banki, Pratappur, Sendra & Narrah mouzas of Bankura-II block under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000673/2023-2024 | 810/BSD | 10/08/2023 | 17/08/2023 | TARUN KUMAR BHATTACHARYYA | 0.95 | 0 | 0 | 100
Total | [13 empty] | 235.77 | 0 | 0