## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Purandapur.) Total House Hold - 502" |  | Junior Engineer | ORD/000323/2020-2021 | 1372/BQA | 08/10/2020 | 07/11/2020 | GOPAL CHANDRA CHOUDHURY | 43.69 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Purandapur.) Total House Hold - 502 . ( MB No - 3997)" |  |  | VCH/001562/2020-2021 | FHTC/283 | 22/02/2021 | 22/02/2021 | GOPAL CHANDRA CHOUDHURY | 36.52 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Junbakra (35) , mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. (part - B) ( MB No - 3948) |  |  | VCH/001539/2020-2021 | FHTC/268 | 05/02/2021 | 05/02/2021 | APEX ENTERPRISE | 26.09 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joyrambati W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001915/2020-2021 | FHTC/294 | 01/03/2021 | 01/03/2021 | TAPAS KUMAR HAZRA | 4.51 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA in Hetiasole mouzas of Khatra-Hirbandh-Ranibandh W/S Scheme under Khatra Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001917/2020-2021 | FHTC/294 | 01/03/2021 | 01/03/2021 | D. S. ENTERPRISE | 4.8 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 03/03/2021 | EARTH MOVING (INDIA) | 31.31 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Construction & commissioning of FHTC in connection with JAL JEVAN MISSION & Jal Swapna of Joyrambati w/s scheme |  |  | VCH/001914/2020-2021 | FHTC/294 | 01/03/2021 | 01/03/2021 | M/S SACHHIDANANDA MAZUMDAR | 4.67 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Laying extra UPVC pipeline to Cover Gaira, Arjunpur , Bahadurpur , Radhanagar, Moukura Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/000846/2021-2022 |  | 01/09/2021 | 01/09/2021 | SUBHADIP KOLEY | 3.8 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Gaira, Arjunpur, Pairasol, & Bahadurpur.) Total House Hold - 506" |  | Junior Engineer | ORD/000322/2020-2021 | 1371/BQA | 08/10/2020 | 07/11/2020 | GOPAL CHANDRA CHOUDHURY | 43.69 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Sinking of 01 (One) no. 200 mm X 165 mm dia.X 258 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000646/2022-2023 | 578/BQA | 17/03/2023 | 16/04/2023 | SINGHA ENTERPRISE | 3.93 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | SM/06807 | Retrofitting | Laying HDPE Pipe Line from Chatarkanali OHR site to Bahadurpur,to increase presure in Bahadurpur & Bagrakonda mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000443/2021-2022 | 511/BQA | 10/03/2022 | 09/04/2022 | SOUMITRA BOSE | 23.15 | 0 | 0 | 0
Total | [13 empty] | 226.14 | 0 | 0