## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Kanchanpur (PART) Total House Hold - 507" |  | Junior Engineer | ORD/000326/2020-2021 | 1374/BQA | 08/10/2020 | 07/11/2020 | GOPAL CHANDRA CHOUDHURY | 42.58 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Laying extra new UPVC pipeline to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I , II & Barjora Block W/S Scheme ( BRGF Ph-I project) under Bankura Sadar Sub Division of Bankura Division PHE Dte. |  |  | VCH/000844/2021-2022 |  | 01/09/2021 | 01/09/2021 | GOPAL CHANDRA CHOUDHURY | 4.19 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Laying of M.S pipeline for crossing bridge to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura I II and Barjora Block ( BRGF ph -I) under Bankura Sadar Sub Division of Bankura Division PHE Dte. |  |  | VCH/000845/2021-2022 |  | 01/09/2021 | 01/09/2021 | GOPAL CHANDRA CHOUDHURY | 1.98 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Laying extra UPVC pipe line to cover Purandarpur & Kanchanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000129/2021-2022 |  | 21/04/2021 | 21/04/2021 | GOPAL CHANDRA CHOUDHURY | 4.35 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR - Arjunpur no .of Mouza :- 05 etc , Total House Hold -1013" |  |  | VCH/001414/2020-2021 |  | 01/03/2021 | 01/03/2021 | TAPAS DEY | 0.32 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Kanchanpur (PART), Dhansimla, Paschim Ratanpur & Kadmaghati) Total House Hold - 506 ( MB No - 3993)" |  |  | VCH/001422/2020-2021 |  | 01/03/2021 | 01/03/2021 | GOPAL CHANDRA CHOUDHURY | 37.09 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Laying extra UPVC pipe line to cover Kadmaghati, Kanchanpur (Part) Paschim Ratanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000135/2021-2022 |  | 21/04/2021 | 21/04/2021 | GOPAL CHANDRA CHOUDHURY | 4.66 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Shyampur (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 1, Shyampur (PART) Total House Hold - 75. , (1) Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1)under Saltora- Chhatna W/S Scheme (BRGF ph - I project) |  |  | VCH/000245/2021-2022 | FHTC/06 | 23/04/2021 | 23/04/2021 | RUFIKUL MONDAL | 3.92 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR - Arjunpur no .of Mouza :- 05 etc , Total House Hold -1008" |  |  | VCH/001413/2020-2021 |  | 01/03/2021 | 01/03/2021 | TAPAS DEY | 0.32 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Kanchanpur (PART), Dhansimla, Paschim Ratanpur & Kadmaghati) Total House Hold - 506" |  | Junior Engineer | ORD/000324/2020-2021 | 1373/BQA | 08/10/2020 | 07/11/2020 | GOPAL CHANDRA CHOUDHURY | 42.54 | 0 | 0 | 100
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 145 | Assistant Engineer |  | ORD/000010/2020-2021 | 611/BQA | 10/02/2021 | 12/03/2021 | SWAPAN KUMAR DE | 9.83 | 2.46 | 25 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 4 nos. i.e. Chanchar-144 (Habitation's Name: CHANCHAR BAURIPARA, CHANCHAR NAPITPARA & NAMOPARA, CHANCHAR UPARPARA & TELIPARA, CHANCHAR LAGAPARA, CHANCHAR DANGAPARA, CHANCHAR TELIPARA & ADIBASHIPARA), Kadamdiha-145 (Habitation's Name: KADAMDIHA), Uparamdahara-146 (Habitation's Name: UPAR AMDAHARA) & Amdahara-147 (Habitation's Name: AMDAHARA UTTARPARA & AMDAHARA DAKSHINPARA) , Total House Hold - 60 out of 921. |  | Junior Engineer | ORD/000150/2020-2021 | 58/VSD | 10/02/2021 | 03/03/2021 | AJIT KUMAR DUTTA | 4.82 | 3.64 | 75.49 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Guniada (1) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000131/2020-2021 | 188/BQA | 18/01/2021 | 17/02/2021 | DEBAKI RANJAN SARKAR | 27.87 | 3.56 | 12.77 | 90
14 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43 , Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 135 | Assistant Engineer |  | ORD/000015/2020-2021 | 616/BQA | 10/02/2021 | 12/03/2021 | MRITYUNJOY HAZRA | 9.84 | 3.54 | 35.97 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | SM/06808 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.48 | 0.21 | 0
Total | [13 empty] | 428.79 | 13.68 | 3.19