## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Kotasol (108) , Chiltere (109) & Jhola (110) mouza by retrofitting zone - ll piped water supply for Chiltore & its adjoining mouzas at block - Sarenga dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. ( MB No - 3909) |  |  | VCH/001573/2020-2021 | FHTC/280 | 12/02/2021 | 12/02/2021 | GOPAL CHANDRA CHOUDHURY | 33.72 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001991/2020-2021 | FHTC/301 | 15/03/2021 | 15/03/2021 | TAPAS DEY | 0.28 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001996/2020-2021 | FHTC/301 | 15/03/2021 | 15/03/2021 | TAPAS DEY | 0.28 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Laying extra HDPE pipe line to cover Khiraijuri mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001336/2021-2022 |  | 28/09/2021 | 28/09/2021 | SOUMITRA BHATTACHARYA | 4.66 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bankati (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001994/2020-2021 | FHTC/301 | 15/03/2021 | 15/03/2021 | TAPAS DEY | 0.38 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dulapara (231), Asarda (232), Chandpara (233), Laupara (269), Kenduadangri (273) & Benasuli (275) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001856/2020-2021 | FHTC/284 | 03/03/2021 | 03/03/2021 | EARTH MOVING (INDIA) | 31.31 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001998/2020-2021 | FHTC/301 | 15/03/2021 | 15/03/2021 | TAPAS DEY | 0.32 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sonadaha (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001993/2020-2021 | FHTC/301 | 15/03/2021 | 15/03/2021 | TAPAS DEY | 0.26 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Laying extra HDPE pipe line to cover Khiraijuri mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001334/2021-2022 |  | 28/09/2021 | 28/09/2021 | SOUMITRA BHATTACHARYA | 4.51 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | "Name of Work: Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 02, (Karanjora, Lapuria (PART)), Total House Hold - 606" |  | Junior Engineer | ORD/000319/2020-2021 | 1369/BQA | 08/10/2020 | 07/11/2020 | SOUMITRA BHATTACHARYA | 41.67 | 0 | 0 | 100
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" |  | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 07/11/2020 | SOUMITRA BHATTACHARYA | 41.63 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Laying HDPE Pipe Line from Kendboni to Lapuria Village & Garakusum village to increase presure in Lapuria & Garakusum mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (ZONE-P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000136/2022-2023 | 472/BSD | 06/06/2022 | 21/06/2022 | ASHIS KUMAR SAMANTA | 4.95 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | SM/06814 | Retrofitting | Laying HDPE Pipe Line to increase pressure at lapuria mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000436/2022-2023 | 622/BSD | 16/08/2022 | 06/09/2022 | ASHIS KUMAR SAMANTA | 3.76 | 0 | 0 | 100
Total | [13 empty] | 167.7 | 0 | 0