## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Laying extra UPVC pipe line to cover Khejurbedia, Radhanagar, Bagrakonda, Upardihi Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte |  |  | VCH/001132/2021-2022 | FHTC/23 | 23/07/2021 | 23/07/2021 | GOPAL CHANDRA CHOUDHURY | 3.37 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Laying extra UPVC pipe line to cover Kadmaghati, Kanchanpur (Part) Paschim Ratanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , |  |  | VCH/001133/2021-2022 | FHTC/23 | 23/07/2021 | 23/07/2021 | GOPAL CHANDRA CHOUDHURY | 4.66 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-01(Kuldiha ), Total House Hold -233 |  |  | VCH/002510/2021-2022 | FHTC/3 | 03/02/2022 | 03/02/2022 | TAPAS PAL | 2.49 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 04 nos, (Ramdihi, Choto Kalajharia, Radharaman Pur, Barokalojuria, ), Total House Hold - 429.' |  |  | VCH/002668/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | BISWARUP BOSE | 2.84 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Baikunthapurl (Part), Total House Hold- 72 (Sl No of Work- 05) |  |  | VCH/002508/2021-2022 | FHTC/3 | 03/02/2022 | 03/02/2022 | SHOVAN DEY | 0.56 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-A ) , Total House Hold -124 ( Sl .No.- 1) |  |  | VCH/002670/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | SUBHADIP KOLEY | 0.89 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Baikunthapurl (Part), Total House Hold- 72 (Sl No of Work- 06) |  |  | VCH/002509/2021-2022 | FHTC/3 | 03/02/2022 | 03/02/2022 | M/S NAYAN BARDHAN | 0.59 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Asansola (Part- B), Total House Hold -169 |  |  | VCH/002669/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | DAUD ALI KHAN | 0.48 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Kulpat, Kesia,& Bhedua(Part), Total House Hold - 435" |  | Junior Engineer | ORD/000382/2020-2021 | 1782/BQA | 09/12/2020 | 08/01/2021 | PARTHA PRATIM CHATAIT | 39.65 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Badra,Gopalpur, Bhedua(Part), Total House Hold - 435" |  | Junior Engineer | ORD/000383/2020-2021 | 1783/BQA | 09/12/2020 | 08/01/2021 | GOUTAM BHOWMIK | 39.71 | 0 | 0 | 100
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | SM/06816 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyampur (44), Jugidangra (47) & Rasikpur (48) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000347/2020-2021 | 1772/BQA | 09/12/2020 | 08/01/2021 | M/S TARUN KUMAR PATRA | 23.94 | 11.28 | 47.12 | 20
Total | [13 empty] | 119.18 | 11.28 | 9.47