## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Laying extra UPVC pipe line to cover Kesiakole Mouza for Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) TELEBEDIA (Zone - M) under Bankura- II Block |  |  | VCH/001479/2021-2022 |  | 08/10/2021 | 08/10/2021 | PARAMESWAR CHOWDHURY | 3.95 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Laying extra UPVC pipe line to cover Purandarpur & Kanchanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001134/2021-2022 | FHTC/23 | 23/07/2021 | 23/07/2021 | GOPAL CHANDRA CHOUDHURY | 4.35 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Extension of UPVC distribution of Cherabastar (Zone - K) to cover Sapagara village under Bankura I, II & Barjora Block water supply scheme (BRGF Phase - I) project under Bankura Division, PHE Dte. |  |  | VCH/001136/2021-2022 | FHTC/23 | 23/07/2021 | 23/07/2021 | SUBHADIP KOLEY | 4.72 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Laying extra UPVC pipe line to cover Kadmaghati, Kanchanpur (Part) Paschim Ratanpur Mouzas for Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Arjunpur (Zone - N) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , |  |  | VCH/001133/2021-2022 | FHTC/23 | 23/07/2021 | 23/07/2021 | GOPAL CHANDRA CHOUDHURY | 4.66 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) & KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Bankura- II, Name of OHR- 1) Tilabedia, 2) Khyerkanali, No. of Mouza :- 25 nos (Mouladanga, Mithila, Jagannathbati, raghunathpur, Manoharpur, Mohanpur, Kesekol, Domanbandhi, Kumuria, Tilabedia, Kamladanga, Bambanpur, Nabada, Sibarampur, Churamonipur, Khyerkanali, Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalaphar, Kaljuri, Muraboni & Rasiknagarpur), Total House Hold = 3931 nos. |  |  | VCH/001337/2021-2022 |  | 28/09/2021 | 28/09/2021 | TAPAS DEY | 1.24 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Bandyagal, No.of Mouza :- Palsora,(Part) , Kalai, Total House Hold - 320., |  |  | VCH/001562/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | ZAKIR HOSSAIN MONDAL | 10.18 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haroka, No.of Mouza :- 2 nos, (Latulia, Lechara) , Total House Hold - 233 |  |  | VCH/001487/2021-2022 | FHTC/03 | 03/11/2021 | 03/11/2021 | BEAUTY CHATTERJEE | 7.46 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  |  | VCH/002299/2021-2022 | FHTC/31 | 31/01/2022 | 31/01/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.91 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 05, (Kesekol (PART), Domanbandhi, Kumuria, Tilabedia & Kamladanga), Total House Hold - 516 |  | Junior Engineer | ORD/000066/2020-2021 | 469/BQA | 05/02/2021 | 07/03/2021 | PARAMESWAR CHOWDHURY | 37.2 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 01, (Kesekol (PART), Total House Hold - 517 ( Sl .No.- 20 ) |  | Junior Engineer | ORD/000176/2020-2021 | 719/BQA | 19/02/2021 | 21/03/2021 | PARAMESWAR CHOWDHURY | 37.25 | 0 | 0 | 100
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza :- 1 no. i.e. Radhanagr-43, Habitation's Name : Biswaspara & Thakurpara, Hospitalpara, Sharmapara & Jharmunnyapara, Bazarpara, Sibtala, Kharpukur Bagdipara, Stidanga Muchipara, Roypara, Saradapally, Jangrapara, Pausa Para, Sayerpara, Loharpara, Dompara, Thanagora, Sahapara, Adibasipara, Barukur Bagdipara, Total House Hold - 130 |  | Junior Engineer | ORD/000021/2020-2021 | 617/BQA | 10/02/2021 | 12/03/2021 | I.R.CONSTRUCTION | 9.86 | 9.4 | 95.29 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 |  | Junior Engineer | ORD/000405/2020-2021 | 863/BQA | 25/02/2021 | 27/03/2021 | NAYAN BARDHAN | 14.75 | 1.69 | 11.44 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | SM/07237 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 04, Chhatatola, Phaspa, Namosusunia, Susunia Pahar Total House Hold - 322 |  | Junior Engineer | ORD/000053/2020-2021 | 460/BQA | 05/02/2021 | 07/03/2021 | I.R.CONSTRUCTION | 28.91 | 8.58 | 29.7 | 95
Total | [13 empty] | 168.43 | 19.67 | 11.68