## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | SM/07246 | Retrofitting | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 03 (Balia, Barabagan & Kasibediya (PART) Total House Hold -399 | Assistant Engineer | Junior Engineer | ORD/000189/2020-2021 | 2130/BQA | 31/12/2020 | 30/01/2021 | KHAN ENTERPRISE | 44.34 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | SM/07246 | Retrofitting | Estimate for Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 02 ( Kasibediya (PART) & Chingra.) Total House Hold -398 |  | Junior Engineer | ORD/000190/2020-2021 | 2131/BQA | 31/12/2020 | 30/01/2021 | KHAN ENTERPRISE | 44.28 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | SM/07246 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 4.54 | 1.93 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | SM/07246 | Retrofitting | Laying HDPE Pipe Line from Beladi more to Barabagan Junior High School to Cover Balia, Basulitora, Rangametya mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone -W) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ( Part-I ) |  | Junior Engineer | ORD/000450/2021-2022 | 572/BQA | 15/03/2022 | 29/04/2022 | PARAMESWAR CHOWDHURY | 21.15 | 17.4 | 82.28 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | SM/07246 | Retrofitting | Laying HDPE Pipe Line from Beladi more to Barabagan Junior High School to Cover Balia, Basulitora, Rangametya mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone -W) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ( Part-II ) |  | Junior Engineer | ORD/000452/2021-2022 | 573/BQA | 15/02/2022 | 01/04/2022 | AMITAVA CHAKRABORTY | 21.15 | 17.36 | 82.09 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | SM/07246 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Bandyagal (Zone - F) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Bandyagal, (Zone-F ) No. of Mouza :- 02 no, Arrah (Part), Khudrabanagram Total House Hold - 383. |  |  | VCH/002452/2021-2022 | FHTC/1 | 01/02/2022 | 01/02/2022 | NAYAN BARDHAN | 28.49 | 0 | 0 | 0
Total | [13 empty] | 393.89 | 39.3 | 9.98