## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 03 (Darpanagar, Urama & Pathrabid,, Total House Hold - 464 |  | Junior Engineer | ORD/000039/2020-2021 | 641/BQA | 10/02/2021 | 12/03/2021 | PRINCE INDUTRIES (INDIA) | 43.55 | 79.28 | 182.05 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 07 ( Kapista, Domnageria, Muradihi, Pachirdanga, Bhola, Kantakuli & Jagatraydihi), Total House Hold - 454 |  | Junior Engineer | ORD/000040/2020-2021 | 642/BQA | 10/02/2021 | 12/03/2021 | PRINCE INDUTRIES (INDIA) | 43.08 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Damodarpur), Total House Hold -226 ( Sl .No.- 7) |  |  | VCH/002802/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SARKAR CONSTRUCTION | 1.49 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 03 (Kanchanpur(PART) ,Kalapani & Nirshce), Total House Hold -476 |  |  | VCH/002801/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | ASOKE BHATTACHARYYA | 2.57 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Laying HDPE Pipe Line with in Pachirdang Village to increse pressure in Pachirdanga mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000441/2021-2022 | 509/BQA | 10/03/2022 | 09/04/2022 | M/S BANERJEE & BANERJEE | 14.41 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Laying balance HDPE Pipe Line with in Pachirdang Village to increase pressure in Pachirdanga mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000512/2022-2023 | 59/BSD | 24/01/2023 | 14/02/2023 | M/S BANERJEE & BANERJEE | 0.96 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 01/08/2022 | BEAUTY CHATTERJEE | 4.95 | 0.11 | 2.3 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | SM/07250 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 |  | Junior Engineer | ORD/000405/2020-2021 | 863/BQA | 25/02/2021 | 27/03/2021 | NAYAN BARDHAN | 14.75 | 23.37 | 158.46 | 0
Total | [13 empty] | 125.76 | 102.76 | 81.72