## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  | Junior Engineer | ORD/000292/2021-2022 | 954/ BSD | 05/10/2021 | 20/10/2021 | GOPAL CHANDRA CHOUDHURY | 4.72 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Laying of HDPE pipe line near Sitalpur village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  | Junior Engineer | ORD/000293/2021-2022 | 955/ BSD | 05/10/2021 | 20/10/2021 | GOPAL CHANDRA CHOUDHURY | 4.1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART- B) |  | Junior Engineer | ORD/000296/2021-2022 | 844/ BSD | 18/08/2021 | 02/09/2021 | GOPAL CHANDRA CHOUDHURY | 4.79 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART-A) |  | Junior Engineer | ORD/000295/2021-2022 | 843/ BSD | 18/08/2021 | 02/09/2021 | GOPAL CHANDRA CHOUDHURY | 4.84 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No(Direct supply), No.of Mouza :- 02 nos, (Bilmalpur , Bamandihi,), Total House Hold -690 nos |  |  | VCH/000268/2022-2023 | FHTC/18 | 18/04/2022 | 18/04/2022 | RANABIR CHATTERJEE | 25.21 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Laying extra upvc pipe line to cover Dhapal & laxman pur for retrofittimg works for creation of FHTC OF Tilabad (Zone -F) OF Saltora Block under Saltora -Chhatna w/s scheme |  |  | VCH/002681/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | SANDHYA DEY | 4.97 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Laying extra HDPE pipeline to cover Jaynagar (47) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Hatikheda) Zone - I under Khatra Sub - Division of Bankura Division, PHE Dte. Block - Ranibandh , dist - Bankura part - B |  |  | VCH/002682/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | M/S TARUN KUMAR PATRA | 2.74 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  |  | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | UNICON INDIA | 152 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 10) |  |  | VCH/002815/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHANKAR BANERJEE | 3.53 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), Total House Hold -972 |  |  | VCH/002305/2021-2022 | FHTC/04 | 04/01/2022 | 04/01/2022 | M/S TARUN KUMAR PATRA | 73.08 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | SM/07251 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 02 nos, (Mouladanga & Mithila), Total House Hold - 519.. ( Sl .No.- 19) |  | Junior Engineer | ORD/000175/2020-2021 | 718/BQA | 19/02/2021 | 21/03/2021 | PARAMESWAR CHOWDHURY | 37.42 | 44.09 | 117.84 | 0
Total | [13 empty] | 317.39 | 44.09 | 13.89