## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-E) Total House Hold -102 |  | Junior Engineer | ORD/000263/2020-2021 | 2062/BQA | 29/12/2020 | 28/01/2021 | GOUTAM GHOSH | 10.52 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-F) Total House Hold -101 |  | Junior Engineer | ORD/000264/2020-2021 | 2063/BQA | 29/12/2020 | 28/01/2021 | GOUTAM GHOSH | 10.44 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-D) Total House Hold -117 |  | Junior Engineer | ORD/000262/2020-2021 | 2061/BQA | 29/12/2020 | 28/01/2021 | JAGADISH BANERJEE | 12.1 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-01 (Talanjuri (PART-A) Total House Hold -114 |  | Junior Engineer | ORD/000252/2020-2021 | 2058/BQA | 29/12/2020 | 28/01/2021 | JAGADISH BANERJEE | 11.87 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR:- Dhaban, No.of Mouza :- 1, Kumirdoha (PART) Total House Hold - 65. , |  |  | VCH/000266/2021-2022 | FHTC/12 | 23/04/2021 | 23/04/2021 | KABISH KUMAR GHOSH | 4.34 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Jagadalla , Anchuri , Chaturdihi , Adharthol , & Kustora, |  |  | VCH/000274/2021-2022 | FHTC/12 | 23/04/2021 | 23/04/2021 | TAPAS DEY | 1.77 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Total House Hold -75 ( MB No - 4020) |  |  | VCH/001427/2020-2021 |  | 01/03/2021 | 01/03/2021 | ASHISH PAUL | 4.56 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-F) Total House Hold -101 ( MB No - 4023)" |  |  | VCH/001424/2020-2021 |  | 01/03/2021 | 01/03/2021 | GOUTAM GHOSH | 7.64 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-D) Total House Hold -117 ( MB No - 4022)" |  |  | VCH/001435/2020-2021 |  | 01/03/2021 | 01/03/2021 | JAGADISH BANERJEE | 9.26 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | "Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-E) Total House Hold -102 ( MB No - 4023)" |  |  | VCH/001425/2020-2021 |  | 01/03/2021 | 01/03/2021 | GOUTAM GHOSH | 7.91 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-01 (Talanjuri (PART-A) Total House Hold -114 ( MB No - 4022)" |  |  | VCH/001434/2020-2021 |  | 01/03/2021 | 01/03/2021 | JAGADISH BANERJEE | 8.2 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | "Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-C) Total House Hold -116 . ( MB No - 3722)" |  |  | VCH/001438/2020-2021 |  | 01/03/2021 | 01/03/2021 | SUBHANKAR BANERJEE | 9.19 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-B) Total House Hold -115 . ( MB No - 3722)" |  |  | VCH/001437/2020-2021 |  | 01/03/2021 | 01/03/2021 | SUBHANKAR BANERJEE | 8.38 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR:- Dhaban, No.of Mouza :- 1, Kumirdoha (PART) Total House Hold - 65. , |  |  | VCH/000268/2021-2022 | FHTC/12 | 23/04/2021 | 23/04/2021 | SIMA KUMBHAKAR | 3.6 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Benda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Abantika, No. of Mouza :- 03 nos. i.e. Abantika- 88 , Belthya- 89 & Deuli- 91, Total House Hold - 733 |  |  | VCH/002416/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | S B ASSOCIATES | 41.78 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-C) Total House Hold -116 |  | Junior Engineer | ORD/000254/2020-2021 | 2060/BQA | 29/12/2020 | 28/01/2021 | SUBHANKAR BANERJEE | 11.93 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-B) Total House Hold -115 |  | Junior Engineer | ORD/000253/2020-2021 | 2059/BQA | 29/12/2020 | 28/01/2021 | SUBHANKAR BANERJEE | 11.8 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | SM/07255 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 2.54 | 1.08 | 0
Total | [13 empty] | 409.8 | 2.54 | 0.62