## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Namonahar), Total House Hold -413 |  | Junior Engineer | ORD/000216/2020-2021 | 2033/BQA | 29/12/2020 | 28/01/2021 | ASHISH KUMAR SAMANTA | 41.33 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 06(Narricha, Bhabanipur, Baliguma, Sapkrrara, Unara & Dharampu) Total House Hold -404 |  | Junior Engineer | ORD/000219/2020-2021 | 2034/BQA | 29/12/2020 | 28/01/2021 | ASHOKE BHATTACHARYYA | 40.43 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Barapukura), Total House Hold -114 |  | Junior Engineer | ORD/000221/2020-2021 | 2035/BQA | 29/12/2020 | 28/01/2021 | TAPAN KUMAR SARKAR | 11.41 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Barapukura), Total House Hold -114 |  |  | VCH/001620/2020-2021 |  | 15/03/2021 | 15/03/2021 | TAPAN KUMAR SARKAR | 10.23 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Laying extra HDPE pipe line to cover malindasi mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joukrishnapur zone - l under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  |  | VCH/001558/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | RUFIKUL MONDAL | 4.65 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Laying extra UPVC pipeline to cover Tentulia (27) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  |  | VCH/001553/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | GOURANGA CHATTERJEE | 2.17 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KOTALPUKUR (Zone - B)) . Name.of Mouza :- 01 no., Rajprasadpur (Part), |  |  | VCH/001555/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | RANABIR CHATTERJEE | 4.78 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Indas W/S Scheme under Bishnupur Sub-Division, PHE Dte. |  |  | VCH/001559/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | SWAPAN KUMAR DE | 6.15 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Laying extra HDPE pipe line to cover malindasi mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI(P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  |  | VCH/001556/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | SOUMITRA BHATTACHARYA | 4.81 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Supplying laying by UPVC pipe for distribution network along with ancillary works at village karbhanga due to strengthening widening of Sarenga Chowrasta more to Goaltore Road under Gargaria Zone -B water supply scheme (BRGF phase -I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. sl no - 13 |  |  | VCH/001502/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | UTTAM KUMAR SINHAMAHAPATRA | 4.95 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Jamda (98) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15), |  |  | VCH/001552/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | ASOKE KUMAR SAHU | 1.61 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhadkidihi (92) and Puada (94) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 222 Nos. , |  |  | VCH/001554/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | BEAUTY CHATTERJEE | 12.84 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Sonareka (Part), Total House Hold- 70 (Sl No of Work- 09) |  |  | VCH/001557/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | MD. AFSAR ALI | 0.59 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Malcharar (100) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) |  |  | VCH/002288/2021-2022 | FHTC/31 | 31/01/2022 | 31/01/2022 | TAPAN KUMAR MANDAL | 4.36 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) |  |  | VCH/002812/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHANKAR BANERJEE | 0.27 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002813/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHANKAR BANERJEE | 0.25 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Kanchanpur (PART), Dhansimla, Paschim Ratanpur & Kadmaghati) Total House Hold - 506' |  |  | VCH/002749/2021-2022 | FHTC/3 | 03/03/2022 | 03/03/2022 | GOPAL CHANDRA CHOWDHURY | 3.89 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) |  |  | VCH/002814/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHANKAR BANERJEE | 0.28 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  |  | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 10/01/2023 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | SM/07257 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 0.56 | 0.24 | 0
Total | [13 empty] | 424.09 | 0.56 | 0.13