## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | SM/07259 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 03 (Kanchanpur(PART) ,Kalapani & Nirshce), Total House Hold -476 |  | Junior Engineer | ORD/000232/2020-2021 | 2043/BQA | 29/12/2020 | 28/01/2021 | ASHOKE BHATTACHARYYA | 42.51 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | SM/07259 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 02 (Koskunda & Kanchanpur(PART)), Total House Hold -479 |  | Junior Engineer | ORD/000231/2020-2021 | 2042/BQA | 29/12/2020 | 28/01/2021 | ASHISH KUMAR SAMANTA | 42.75 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | SM/07259 | Retrofitting | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KANCHANPUR (Zone - C), Name of mouza (Koskunda) |  |  | VCH/001352/2021-2022 |  | 28/09/2021 | 28/09/2021 | ASHISH KUMAR SAMANTA | 4.03 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | SM/07259 | Retrofitting | Extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - KANCHANPUR (Zone - C), Name of mouza (Nirsha) |  |  | VCH/001353/2021-2022 |  | 28/09/2021 | 28/09/2021 | ASOKE BHATTACHARYYA | 4.01 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | SM/07259 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 21/03/2021 | M/S TARUN KUMAR PATRA | 96.69 | 16.07 | 16.62 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | SM/07259 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 17/02/2021 | EARTHMOVING (INDIA) | 39.43 | 45.12 | 114.41 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | SM/07259 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 03 nos, (Kherosol, Emokundi & Gopinathpur), Total House Hold - 527." |  | Junior Engineer | ORD/000343/2020-2021 | 1768/BQA | 09/12/2020 | 08/01/2021 | GOUTAM BHATTACHRYYA | 37.17 | 64.08 | 172.4 | 0
Total | [13 empty] | 266.58 | 125.27 | 46.99