## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 03(Enayetpur , Namoghansara , Ekariya ), Total House Hold - 204 |  | Junior Engineer | ORD/000028/2020-2021 | 630/BQA | 10/02/2021 | 12/03/2021 | AJIT KUMAR PAUL | 15.55 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-D) , Total House Hold - 154 |  | Junior Engineer | ORD/000247/2020-2021 | 2054/BQA | 29/12/2020 | 28/01/2021 | TAPAS PAL | 12.14 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 ,Gadardihi (PART-B ), Total House Hold - 115 |  | Junior Engineer | ORD/000245/2020-2021 | 2052/BQA | 29/12/2020 | 28/01/2021 | BEAUTY CHATTERJEE | 9.12 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-C) Total House Hold - 150 |  | Junior Engineer | ORD/000246/2020-2021 | 2053/BQA | 29/12/2020 | 28/01/2021 | GOURANGA CHATTERJEE | 11.86 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gadardihi (PART-E), Total House Hold - 114 |  | Junior Engineer | ORD/000249/2020-2021 | 2055/BQA | 29/12/2020 | 28/01/2021 | BEAUTY CHATTERJEE | 9 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 04 (Kurulia ,Majdangra , Gadardihi Balarampur, & Gobindapur(PART-B) ), Total House Hold - 155 |  | Junior Engineer | ORD/000251/2020-2021 | 2057/BQA | 29/12/2020 | 28/01/2021 | AJIT KUMAR PAUL | 12.26 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Gadardihi , Salulia, Joyunga, Joykrishanapur , No Of Mouzas-73 , Total House Hold - 11815 |  |  | VCH/000273/2021-2022 | FHTC/12 | 23/04/2021 | 23/04/2021 | TAPAS DEY | 2.19 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-C) Total House Hold - 150 |  |  | VCH/001418/2020-2021 |  | 01/03/2021 | 01/03/2021 | GOURANGA CHATTERJEE | 10.33 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Household Survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- Gadardihi , Salulia, Joyunga, Joykrishanapur , No Of Mouzas-73 , Total House Hold - 11815 |  |  | VCH/001613/2020-2021 |  | 15/03/2021 | 15/03/2021 | TAPAS DEY | 2.19 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  |  | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Laying extra UPVC pipeline to cover Paryasa (169) & Purnapani Chhota Tung (170) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) |  |  | VCH/002426/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | UNITED TRADERS | 2.87 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . Name of mouza -Bandarkoda |  |  | VCH/002418/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | SIB SANKAR CHOWDHURY | 4.35 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10) |  |  | VCH/002423/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | UNITED TRADERS | 3.72 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) , Name of mouza -Kodma , (Part-A) |  |  | VCH/002419/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | SIB SANKAR CHOWDHURY | 4.35 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part -B) (Sl. No. 13) |  |  | VCH/002432/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | UNITED TRADERS | 4 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 09) |  |  | VCH/002420/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | UNITED TRADERS | 4.96 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 12) |  |  | VCH/002428/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | UNITED TRADERS | 4.89 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, ( Simla, Bank simul, Nekrakuada ) Total House Hold - 499 |  |  | VCH/003100/2021-2022 | FHTC/28 | 28/03/2022 | 28/03/2022 | M/S TARUN KUMAR PATRA | 37.54 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Palsona more to Ramchandrapur High School under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Palsona & Ramchandrapur |  |  | VCH/002656/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | RUFIKUL MONDAL | 4.8 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Extra retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) of GADARDIHI (Zone- E) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora ,Total House Hold -02nos. (Gadhardihi PHC, Jaganathpur SHC) | Assistant Engineer | Junior Engineer | ORD/000824/2022-2023 | 215/BSD | 28/02/2023 | 15/03/2023 | GORAI CONSTRUCTION | 0.92 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gobindapur (Part -A ), Total House Hold - 145 |  | Junior Engineer | ORD/000250/2020-2021 | 2056/BQA | 29/12/2020 | 28/01/2021 | SUBHANKAR BANERJEE | 11.43 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , Gadardihi (PART-A ), Total House Hold - 200 |  | Junior Engineer | ORD/000243/2020-2021 | 2051/BQA | 29/12/2020 | 28/01/2021 | SUBHANKAR BANERJEE | 15.84 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | SM/07261 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 1.53 | 0.65 | 0
Total | [13 empty] | 455.93 | 1.53 | 0.34