## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam | SM/07264 | Retrofitting | Laying HDPE Pipe Line from Bhagabundh to PatalKhuri (Bridge) to Cover Patal Khuri mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000290/2022-2023 | 506/BSD | 12/07/2022 | 27/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.63 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam | SM/07264 | Retrofitting | Laying HDPE Pipe Line from PatalKhuri (Bridge) to Patalkhuri village to cover Patal Khuri mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000292/2022-2023 | 508/BSD | 12/07/2022 | 27/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.16 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam | SM/07264 | Retrofitting | Laying of 150 mm dia. DI pipe line for Ekteswar W/S Scheme & Restoration & laying of M.S. pipeline near Rajagram Bridge to Cover up Nandigram Village under Bankura Sadar Sub - Division of Bankura Division P.H.E. Dte. |  | Junior Engineer | ORD/000305/2022-2023 | 465/BSD | 06/06/2022 | 21/06/2022 | SAMIRUDDIN KHAN | 4.36 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam | SM/07264 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 05 Nos. ( Patalkuri, Nandigram, Damadarpur, Agaya & Manusmara. ) Total House Hold - 1086 , 1086/2=543 (PART-B) | Assistant Engineer | Junior Engineer | ORD/000832/2022-2023 | 690/BQA | 30/03/2023 | 14/05/2023 | M/S KHAN ENTERPRISE | 27.33 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam | SM/07264 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 05 Nos. ( Patalkuri, Nandigram, Damadarpur, Agaya & Manusmara. ) Total House Hold - 1086, 1086/2=543 (PART-A) | Assistant Engineer | Junior Engineer | ORD/000533/2022-2023 | 689/BQA | 30/03/2023 | 01/04/2026 | ASHOKE KUMAR DEY | 27.33 | 0 | 0 | 0
Total | [13 empty] | 67.81 | 0 | 0