## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Shyamnagar (22) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) |  | Junior Engineer | ORD/000460/2020-2021 | 119/KSD | 11/02/2021 | 21/02/2021 | BIKASH MANDAL | 2.7 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mahaldanga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 16) |  | Junior Engineer | ORD/000374/2020-2021 | 26/KSD | 14/01/2021 | 29/01/2021 | ASOKE KUMAR SAHU | 4.12 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mahaldanga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 17) |  | Junior Engineer | ORD/000376/2020-2021 | 27/KSD | 14/01/2021 | 29/01/2021 | ASOKE KUMAR SAHU | 4.08 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahmadanga (33) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) |  | Junior Engineer | ORD/000361/2020-2021 | 13/KSD | 14/01/2021 | 29/01/2021 | UNITED TRADERS | 4.52 | 0.16 | 3.49 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahmadanga (33) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) |  | Junior Engineer | ORD/000362/2020-2021 | 14/KSD | 14/01/2021 | 29/01/2021 | UNITED TRADERS | 4.39 | 0.13 | 2.97 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahmadanga (33) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 5) |  | Junior Engineer | ORD/000363/2020-2021 | 15/KSD | 14/01/2021 | 29/01/2021 | UNITED TRADERS | 4.29 | 0.04 | 0.93 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mahaldanga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 15) |  | Junior Engineer | ORD/000373/2020-2021 | 25/KSD | 14/01/2021 | 29/01/2021 | ASOKE KUMAR SAHU | 4.26 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simul Kundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 18) |  | Junior Engineer | ORD/000377/2020-2021 | 28/KSD | 14/01/2021 | 29/01/2021 | SRIKANTA MONDAL | 4.99 | 0.12 | 2.42 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl.No-9) |  |  | VCH/001583/2020-2021 |  | 15/03/2021 | 15/03/2021 | BEAUTY CHATTERJEE | 4.16 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Naria (29), Benagaria (30) & Hirakhon (31) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000669/2021-2022 |  | 16/07/2021 | 16/07/2021 | UTTAM KUMAR SINHAMAHAPATRA | 2.24 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/001455/2021-2022 |  | 08/10/2021 | 08/10/2021 | ASOKE KUMAR SAHU | 3.64 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chanpasol (78) mouzas by Rectrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh water supply scheme ( BRGF Ph-I) at Block- Hirrbandh , Dist Bankura under Jal Swapna & Jal Jeevan mission program me under Khatra Sub-Division of Bankura Division PHE Dte. (Part-C) Sl No-10 |  |  | VCH/001580/2020-2021 |  | 15/03/2021 | 15/03/2021 | GOURANGA CHATTERJEE | 4.03 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl.No-8) |  |  | VCH/001582/2020-2021 |  | 15/03/2021 | 15/03/2021 | BEAUTY CHATTERJEE | 4.14 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34), mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/001453/2021-2022 |  | 08/10/2021 | 08/10/2021 | ASOKE KUMAR SAHU | 2.98 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/001456/2021-2022 |  | 08/10/2021 | 08/10/2021 | ASOKE KUMAR SAHU | 3.35 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Brahmadanga (33) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000670/2021-2022 |  | 16/07/2021 | 16/07/2021 | UNITED TRADERS | 3.36 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chanpasol (78) mouzas by Rectrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh water supply scheme ( BRGF Ph-I) at Block- Hirrbandh , Dist Bankura under Jal Swapna & Jal Jeevan misssion programme under Khatra Sub-Division of Bankura Division PHE Dte. (Part-D) Sl No-11 |  |  | VCH/001579/2020-2021 |  | 15/03/2021 | 15/03/2021 | GOURANGA CHATTERJEE | 3.61 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in simulkundi (77) mouzas by retrofitting zone - E (Naria) of Khatra-Hirbandh-Ranibandh w/s scheme ( BRGF PH - I) at block - Hirbandh under Jal Jeeval Mission (JJM) and Jal Swapna & Jal Jeevan Mission programme under Khatra sub - Division of Bankura Division PHE Dte. |  |  | VCH/001379/2020-2021 |  | 01/03/2021 | 01/03/2021 | SRIKANTA MONDAL | 4.87 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | House hold survey different mouzas of Naria Zone -E OF Khatra-Hirbandh-Ranibandh w/s scheme at Hirbandh Block |  |  | VCH/001736/2020-2021 |  | 19/03/2021 | 19/03/2021 | TAPAS DEY | 0.39 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying extra HDPE pipeline to cover Buriam (112) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) |  |  | VCH/001387/2021-2022 | FHTC/24 | 24/09/2021 | 24/09/2021 | SUBHADIP KOLEY | 2.47 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying extra UPVC pipe line to cover shyamnagar (22) mouza for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ retrofitting Zone - E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000333/2021-2022 |  | 11/05/2021 | 11/05/2021 | BIKASH MANDAL | 2.53 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mahal Danga (34) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/001454/2021-2022 |  | 08/10/2021 | 08/10/2021 | ASOKE KUMAR SAHU | 2.98 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simulkundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) |  | Junior Engineer | ORD/000396/2021-2022 | 746/KSD | 18/11/2021 | 25/11/2021 | SRIKANTA MONDAL | 1.99 | 0 | 0 | 0
24 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Household survey in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 12) |  | Junior Engineer | ORD/000520/2020-2021 | 318/KSD | 29/12/2020 | 28/02/2021 | TAPAS DEY | 0.4 | 0 | 0 | 0
25 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Brahmadanga (33) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 07) |  | Junior Engineer | ORD/000388/2021-2022 | 771/KSD | 25/11/2021 | 10/12/2021 | UNITED TRADERS | 2.5 | 0 | 0 | 0
26 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Mahaldanga (34) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) |  | Junior Engineer | ORD/000333/2021-2022 | 671/KSD | 29/09/2021 | 14/10/2021 | ASOKE KUMAR SAHU | 4.98 | 0 | 0 | 0
27 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Shyamnagar (22) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) |  | Junior Engineer | ORD/000534/2021-2022 | 96/KSD | 10/03/2022 | 20/03/2022 | SUNIL KUMAR MANDAL | 4.73 | 4.7 | 99.41 | 0
28 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying extra UPVC pipeline to cover Birbhandh (183) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) |  |  | VCH/002436/2021-2022 | FHTC/17 | 17/02/2022 | 17/02/2022 | UNITED TRADERS | 3.56 | 0 | 0 | 0
29 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying extra UPVC pipe line to cover Bhedua Purosatyampur, Narrah mouzas for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002879/2021-2022 |  | 16/03/2022 | 16/03/2022 | SELCO | 3.61 | 0 | 0 | 0
30 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Gopbandh, Kantabandh, Elia Narayanpur, & Rautora), Total House Hold - 51 nos. |  |  | VCH/002880/2021-2022 |  | 16/03/2022 | 16/03/2022 | DAUD ALI KHAN | 4.42 | 0 | 0 | 0
31 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 01 no, (Hatjore) Total House Hold - 149 |  |  | VCH/002285/2021-2022 | FHTC/31 | 31/01/2022 | 31/01/2022 | GOUTAM GHOSH | 10.74 | 0 | 0 | 0
32 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simulkundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) |  |  | VCH/002930/2021-2022 | FHTC/21 | 21/03/2022 | 21/03/2022 | SRIKANTA MONDAL | 1.97 | 0 | 0 | 0
33 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Brahma Danga (33), mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/000657/2022-2023 | FHTC/21 | 21/07/2022 | 21/07/2022 | UNITED TRADERS | 1.27 | 0 | 0 | 0
34 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 8) |  | Junior Engineer | ORD/000366/2020-2021 | 18/KSD | 14/01/2021 | 29/01/2021 | BEAUTY CHATTERJEE | 4.5 | 0.13 | 2.86 | 0
35 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 9) |  | Junior Engineer | ORD/000367/2020-2021 | 19/KSD | 14/01/2021 | 29/01/2021 | BEAUTY CHATTERJEE | 4.37 | 0.14 | 3.24 | 0
36 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 10) |  | Junior Engineer | ORD/000368/2020-2021 | 20/KSD | 14/01/2021 | 29/01/2021 | GOURANGA CHATTERJEE | 4.37 | 0.13 | 2.95 | 0
37 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chanpasol (78) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 11) |  | Junior Engineer | ORD/000369/2020-2021 | 21/KSD | 14/01/2021 | 29/01/2021 | GOURANGA CHATTERJEE | 3.87 | 0.1 | 2.49 | 0
38 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagaria (30) & Hirakhon (31) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 7) |  | Junior Engineer | ORD/000365/2020-2021 | 17/KSD | 14/01/2021 | 29/01/2021 | UTTAM KUMAR SINHAMAHAPATRA | 4.38 | 0.19 | 4.34 | 100
39 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyamnagar (22) & Aral Chhota (28) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 12) |  | Junior Engineer | ORD/000370/2020-2021 | 22/KSD | 14/01/2021 | 29/01/2021 | BIKASH MANDAL | 4.97 | 0.08 | 1.62 | 0
40 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyamnagar (22) & Aral Chhota (28) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13) |  | Junior Engineer | ORD/000371/2020-2021 | 23/KSD | 14/01/2021 | 29/01/2021 | TAPAN KUMAR MANDAL | 4.99 | 0.49 | 9.82 | 0
41 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Brahamadanga (33) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | Assistant Engineer |  | ORD/001048/2021-2022 | 743/KSD | 18/11/2021 | 25/11/2021 | UNITED TRADERS | 1.27 | 0 | 0 | 0
42 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 1) | Assistant Engineer |  | ORD/000043/2020-2021 | 11/KSD | 14/01/2021 | 29/01/2021 | UTTAM KUMAR SINHAMAHAPATRA | 4.01 | 0.26 | 6.45 | 25
43 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 |  | Junior Engineer | ORD/000017/2020-2021 | 619/BQA | 10/02/2021 | 12/03/2021 | MUNMUN UPADHYAY | 35.36 | 0.11 | 0.32 | 0
44 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Naria (29) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 2) |  | Junior Engineer | ORD/000360/2020-2021 | 12/KSD | 14/01/2021 | 29/01/2021 | UTTAM KUMAR SINHAMAHAPATRA | 3.93 | 0.32 | 8.12 | 25
45 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagaria (30) & Hirakhon (31) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 6) |  | Junior Engineer | ORD/000364/2020-2021 | 16/KSD | 14/01/2021 | 29/01/2021 | UTTAM KUMAR SINHAMAHAPATRA | 4.56 | 0.16 | 3.49 | 100
46 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Shyamnagar (22) & Aral Chhota (28) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 14) |  | Junior Engineer | ORD/000372/2020-2021 | 24/KSD | 14/01/2021 | 29/01/2021 | SUNIL KUMAR MANDAL | 4.97 | 0.4 | 8.04 | 0
47 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Telebedia, No. of Mouza :- 01 no., Mouladanga (Part), Total House Hold- 60 nos. (Part- B) |  | Junior Engineer | ORD/000465/2021-2022 | 185/BSD | 18/02/2022 | 28/02/2022 | M/S BANERJEE & BANERJEE | 3.48 | 3.48 | 99.8 | 0
48 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying HDPE pipeline from Kankri Jharna More to Barikul Primary School to increase pressure in Barikul (179) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000061/2022-2023 | 1685/BQA | 27/07/2022 | 26/08/2022 | APEX ENTERPRISE | 7.7 | 0.16 | 2.03 | 0
49 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Supply laying & fitting fixing of MS pipe line crossing at Tentulpoha jore & repairing of existing UPVC pipe connection for Tentulpoha village for Maliara (Zone -A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Jal Jeevan Mission (JJM) and JAL SWAPNA Fund) |  | Junior Engineer | ORD/000303/2022-2023 | 557/BSD | 29/07/2022 | 28/08/2022 | SAMIRUDDIN KHAN | 2.85 | 0.6 | 20.96 | 0
50 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Laying balance HDPE Pipe Line with in Pachirdang Village to increase pressure in Pachirdanga mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000512/2022-2023 | 59/BSD | 24/01/2023 | 14/02/2023 | M/S BANERJEE & BANERJEE | 0.96 | 0.8 | 82.95 | 0
51 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Telebedia, No. of Mouza :- 01 no., Mouladanga (Part), Total House Hold- 60 nos. (Part- A) |  | Junior Engineer | ORD/000464/2021-2022 | 184/BSD | 18/02/2022 | 28/02/2022 | GOURANGA CHATTERJEE | 3.5 | 3.47 | 99.3 | 0
52 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 21/03/2021 | M/S TARUN KUMAR PATRA | 96.69 | 25.88 | 26.77 | 0
53 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 17/02/2021 | EARTHMOVING (INDIA) | 39.43 | 5.07 | 12.85 | 0
54 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | SM/07270 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 4.02 | 1.72 | 0
Total | [13 empty] | 592.92 | 51.13 | 8.62