## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 290 |  | Junior Engineer | ORD/000011/2020-2021 | 612/BQA | 10/02/2021 | 12/03/2021 | SWAPAN KUMAR BIT | 19.65 | 14.01 | 71.27 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 140 |  | Junior Engineer | ORD/000009/2020-2021 | 610/BQA | 10/02/2021 | 12/03/2021 | SWAPAN KUMAR BIT | 9.6 | 9.6 | 100 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 289 |  | Junior Engineer | ORD/000012/2020-2021 | 613/BQA | 10/02/2021 | 12/03/2021 | OSMAN SEKH | 18.09 | 10.23 | 56.57 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67, Total House Hold - 166 out of 1275 Part-A (Phase-2) |  | Junior Engineer | ORD/000211/2021-2022 | 3047/BQA | 01/12/2021 | 31/12/2021 | KOUSIK MONDAL | 12.53 | 8.46 | 67.52 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 125 |  | Junior Engineer | ORD/000008/2020-2021 | 609/BQA | 10/02/2021 | 12/03/2021 | OSMAN SEKH | 8.39 | 3.14 | 37.41 | 0
6 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 |  | Junior Engineer | ORD/000017/2020-2021 | 619/BQA | 10/02/2021 | 12/03/2021 | MUNMUN UPADHYAY | 35.36 | 0.93 | 2.63 | 0
7 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, |  |  | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 (Cahndanpur, Swargabati, Gopinathpur), Total House Hold -456, |  |  | VCH/001589/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | MUNMUN UPADHYAY | 33.29 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Laying extra UPVC Pipe Line to Cover chotochaka, sonarekh mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., |  |  | VCH/001590/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | KASTURI ROY | 2.17 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Indas W/S Scheme under Bishnupur Sub-Division, PHE Dte. |  |  | VCH/001559/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | SWAPAN KUMAR DE | 6.15 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Work Order for Laying HDPE pipeline from Dhabani Shib Mandir to Keliapathar village to increase pressure in Keliapathar village in Gobarda (152) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) |  | Junior Engineer | ORD/000107/2022-2023 | 210/KSD | 03/06/2022 | 23/06/2022 | D. S. ENTERPRISE | 4.02 | 3.88 | 96.51 | 0
12 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | SM/07272 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 1.9 | 0 | 0 | 0
Total | [13 empty] | 201.43 | 50.25 | 24.95