## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , Jagannath pur (Part- D), Asansola (Part- A), Total House Hold -170 |  | Junior Engineer | ORD/000209/2020-2021 | 626/BQA | 10/02/2021 | 12/03/2021 | GOUTAM GHOSH | 12.29 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 03 (Kantabandh ,Radharamanpur , Birsing pur ), Total House Hold -166 |  | Junior Engineer | ORD/000019/2020-2021 | 622/BQA | 10/02/2021 | 12/03/2021 | DAUD ALI KHAN | 11.91 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 (Elia Narayan pur , Rautora), Total House Hold -158 |  | Junior Engineer | ORD/000020/2020-2021 | 623/BQA | 10/02/2021 | 12/03/2021 | DAUD ALI KHAN | 11.38 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Asansola (Part- B), Total House Hold -169 |  | Junior Engineer | ORD/000022/2020-2021 | 624/BQA | 10/02/2021 | 12/03/2021 | DAUD ALI KHAN | 12.18 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Jagannath pur (Part- A), Total House Hold -175 |  | Junior Engineer | ORD/000023/2020-2021 | 625/BQA | 10/02/2021 | 12/03/2021 | GOUTAM GHOSH | 12.66 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , (Saldanga , Muktapur ), Total House Hold -253 |  | Junior Engineer | ORD/000027/2020-2021 | 629/BQA | 10/02/2021 | 12/03/2021 | SUBHENDU SEKHAR GORAI | 18.25 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Extra UPVC line of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-18) |  |  | VCH/000877/2021-2022 |  | 07/09/2021 | 07/09/2021 | DAUD ALI KHAN | 3.98 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Supply laying & fitting fixing of GI pipeline crossing at Sali river of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-17) |  |  | VCH/000876/2021-2022 |  | 07/09/2021 | 07/09/2021 | DAUD ALI KHAN | 1.75 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17), |  |  | VCH/001567/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | UNIVERSAL CONSTRUCTION | 37.69 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- (Dadimukha, Saldanga), Total House Hold - 55 nos. |  | Junior Engineer | ORD/000409/2021-2022 | 09/ BSD | 07/01/2022 | 19/01/2022 | SUBHENDU SEKHAR GORAI | 3.96 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Gopbandh, Kantabandh, Elia Narayanpur, & Rautora), Total House Hold - 51 nos. |  | Junior Engineer | ORD/000407/2021-2022 | 15/ BSD | 07/01/2022 | 22/01/2022 | DAUD ALI KHAN | 4.42 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Bankura- I, Name of OHR - Anchuri. No.of Mouza :- 07 ( Kapista, Domnageria, Muradihi, Pachirdanga, Bhola, Kantakuli & Jagatraydihi), Total House Hold - 454 |  |  | VCH/002675/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | PRINCE INDUTRIES (INDIA) | 1.26 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 04 (Gaira, Arjunpur, Pairasol, & Bahadurpur.) Total House Hold - 50 |  |  | VCH/002676/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | GOPAL CHANDRA CHOWDHURY | 1.39 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Extra UPVC pipe line for increase pressure at Jaganathpur Somondal para of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Name of Mouza Jaganathpur) | Assistant Engineer |  | ORD/000495/2022-2023 | 373/BQA | 23/02/2023 | 09/04/2023 | GOURANGA NANDI | 2.08 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Laying of HDPE pipe line from Jagannathpur to Bankuradanga & Muktapur Village to increase pressure in Bankuradanga Mouza & MuktapurMouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000005/2022-2023 | 893/BQA | 18/04/2022 | 18/05/2022 | AMITAVA CHAKRABORTY | 29.71 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Jagannath pur (Part- C), Total House Hold -106 |  | Junior Engineer | ORD/000026/2020-2021 | 628/BQA | 10/02/2021 | 12/03/2021 | GOURANGA NANDI | 7.64 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 ,Jagannath pur (Part- B), Total House Hold -107 |  | Junior Engineer | ORD/000096/2020-2021 | 627/BQA | 10/02/2021 | 12/03/2021 | GOURANGA NANDI | 7.82 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jamthol (PART) Total House Hold- 140 |  | Junior Engineer | ORD/000204/2020-2021 | 989/BQA | 26/02/2021 | 28/03/2021 | MRITYUNJOY HAZRA | 9.83 | 17.13 | 174.21 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | SM/07306 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 01( Napra(Part-A) ), Total House Hold -418 |  | Junior Engineer | ORD/000399/2020-2021 | 857/BQA | 25/02/2021 | 27/03/2021 | SUBHANKAR BANERJEE | 35.1 | 10.64 | 30.31 | 0
Total | [13 empty] | 225.32 | 27.77 | 12.33