## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Gara), Total House Hold -132 |  | Junior Engineer | ORD/000029/2021-2022 | 1798/BQA | 09/07/2021 | 08/08/2021 | SK. ALAMAGIR ALAM | 7.34 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Retrofitting works for creacion of FHTC (Funtcional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Parasia), Total House Hold -155 |  | Junior Engineer | ORD/000024/2021-2022 | 1799/BQA | 09/07/2021 | 08/08/2021 | TAPAN KUMAR UPADHYAY | 9.05 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 02 no, (Jorhira, Arajuri), Total House Hold -447 |  | Junior Engineer | ORD/000053/2021-2022 | 1931 A /BQA | 28/07/2021 | 27/08/2021 | TAPAS PAL | 26.93 | 5.35 | 19.87 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 02 no, (Sanpura, Kalipahari), Total House Hold - 451 |  | Junior Engineer | ORD/000054/2021-2022 | 1931 B / BQA | 28/07/2021 | 27/08/2021 | TARINI CHARAN UPADHYAY | 27.98 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying extra HDPE pipeline to cover Tilabani (39) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No.- 12) |  |  | VCH/001785/2021-2022 | FHTC/29 | 29/10/2021 | 29/10/2021 | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Household survey in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 2), |  |  | VCH/001786/2021-2022 | FHTC/07 | 07/10/2021 | 07/10/2021 | TAPAS DEY | 0.24 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying extra UPVC pipe line to cover Kesiakole Mouza for Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) TELEBEDIA (Zone - M) under Bankura- II Block, |  |  | VCH/001784/2021-2022 | FHTC/28 | 28/10/2021 | 28/10/2021 | PARAMESWAR CHOWDHURY | 3.95 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  |  | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying extra UPVC pipe line to cover Mithila Mouza for Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) TELEBEDIA (Zone - M) under Bankura- II Block, |  |  | VCH/001783/2021-2022 | FHTC/28 | 28/10/2021 | 28/10/2021 | PARAMESWAR CHOWDHURY | 4.65 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- Sanpura (Part) Total House Hold - 59 nos. |  | Junior Engineer | ORD/000069/2022-2023 | 254/KSD | 12/07/2022 | 27/07/2022 | TARINI CHARAN UPADHYAY | 4.36 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No. of Mouza:- 1 no., ( Parasia), Total House Hold -18 nos. (Sl. No. 04) |  | Junior Engineer | ORD/000137/2022-2023 | 251/KSD | 12/07/2022 | 27/07/2022 | TAPAN KUMAR UPADHYAY | 1.4 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Jorehira (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Chhatna, Name of OHR - Jorehira, No.of Mouza :- 01 no., Jorehira (Part), Total House Hold- 75 nos. |  | Junior Engineer | ORD/000312/2021-2022 | 3367/BQA | 31/12/2021 | 30/01/2022 | DURGADAS SINGHA | 5.59 | 5.59 | 99.94 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- Jorehira (Part), Total House Hold - 50 nos. (Sl. No. 12) |  | Junior Engineer | ORD/000084/2022-2023 | 259/KSD | 12/07/2022 | 27/07/2022 | DURGADAS SINGHA | 2.5 | 2.49 | 99.85 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Work Order for Laying Extra UPVC Pipe Line to Cover Jorehira mouza & Dismantaling & reconstruction of concrete for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Sl. No. 18) |  | Junior Engineer | ORD/000086/2022-2023 | 352/KSD | 16/08/2022 | 05/09/2022 | DURGADAS SINGHA | 3.81 | 3.79 | 99.44 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying extra HDPE pipe lineto cover Gorabari & Bansi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002598/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | M/S TARUN KUMAR PATRA | 29.87 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying UPVC pipes for jorehera mouza of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna W/S Scheme (BRGF Ph - I project) |  |  | VCH/001207/2022-2023 | FHTC/15 | 15/09/2022 | 15/09/2022 | TAPAS PAL | 1.52 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | laying extra HDPE pipe line to cover Simia , bank simul mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Chinabari Zone - H under Saltora block Saltora - Chhatna Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte part - A |  |  | VCH/003104/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | M/S TARUN KUMAR PATRA | 4.73 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying extra HDPE pipe lineto cover Gorabari & Bansi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002589/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | M/S TARUN KUMAR PATRA | 4.22 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying extra HDPE pipe lineto cover dadhimukha & Jagdalla mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002588/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | M/S TARUN KUMAR PATRA | 4.48 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | laying extra HDPE pipe line to cover Simia , bank simul mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Chinabari Zone - H under Saltora block Saltora - Chhatna Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte part - B |  |  | VCH/003105/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | M/S TARUN KUMAR PATRA | 4.11 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Jorehira, No. of Mouza:- 1 no., ( Parasia), Total House Hold -18 nos. (Sl. No. 04) |  |  | VCH/001203/2022-2023 | FHTC/28 | 28/09/2022 | 28/09/2022 | TAPAN KUMAR UPADHYAY | 1.39 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Laying HDPE Pipe Line from Parasia air valve to Jirrah village for water supply arrangement at Jirrah village for retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000277/2022-2023 | 07/BQA | 03/01/2023 | 17/02/2023 | BISWARUP BOSE | 26.51 | 14.92 | 56.27 | 0
23 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :-01 (Rajprasadpur (Part), Total House Hold -473 |  | Junior Engineer | ORD/000210/2020-2021 | 2031/BQA | 29/12/2020 | 28/01/2021 | RANABIR CHATTERJEE | 41.02 | 2.46 | 5.99 | 0
24 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHIRA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - JOREHIRA, No. of Mouza :- 01 no., JORHIRA (PART), Total House Hold :- 10 Nos. | Assistant Engineer | Junior Engineer | ORD/000127/2023-2024 | 98/KSD | 28/04/2023 | 28/05/2023 | TAPAS KUMBHAKAR | 0.59 | 0 | 0 | 100
25 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JORE | SM/07310 | Retrofitting | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOREHIRA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - JOREHIRA, No. of Mouza :- 03 no, PARASIA (PART), Jhikuria (PART), kuladabar(PART), Total House Hold :- 12 Nos. | Assistant Engineer | Junior Engineer | ORD/000157/2023-2024 | 102/KSD | 28/04/2023 | 28/05/2023 | TAPAS KUMAR HAZRA | 0.68 | 0 | 0 | 100
Total | [13 empty] | 258.96 | 34.6 | 13.36