## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), Total House Hold -972 |  | Junior Engineer | ORD/000461/2020-2021 | 129/SE/PIU-BANKURA | 24/02/2021 | 26/03/2021 | M/S TARUN KUMAR PATRA | 82.32 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B), No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), (Part-A) |  | Junior Engineer | ORD/000245/2021-2022 | 754/ BSD | 26/07/2021 | 10/08/2021 | M/S TARUN KUMAR PATRA | 3.85 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone- B), No. of Mouza:- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur), (Part- B) |  | Junior Engineer | ORD/000257/2021-2022 | 755/ BSD | 27/07/2021 | 11/08/2021 | M/S TARUN KUMAR PATRA | 4.85 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 3 nos ( Susunia, Ethani, Tulsha (Part). ) Total House Hold - 552 |  |  | VCH/001732/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | M/S BIPUL BANERJEE | 24.12 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  |  | VCH/002379/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | PRADYUMNA KOLEY | 4.71 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) |  |  | VCH/002321/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | PRADYUMNA KOLEY | 3.25 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I, Total House Hold -609 nos. |  |  | VCH/002318/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | ZAKIR HOSSAIN MONDAL | 46 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 |  |  | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 25/12/2021 | UNICON INDIA | 75 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Laying extra HDPE pipeline to cover Ghagra (115) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) |  |  | VCH/002380/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | SUBHADIP KOLEY | 4.99 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 02 churamonipur & bambhanpur Total House Hold - 124 ( Sl .No.-23) |  |  | VCH/002313/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | PRADIP CHAKRABORTY | 9.22 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 nos, sibrampur Total House Hold - 151 |  |  | VCH/002312/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | PRADIP CHAKRABORTY | 11.53 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Madandihi(101) & Malcharar (100) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) |  |  | VCH/002319/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | SUBHADIP KOLEY | 3.99 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 05) |  |  | VCH/002320/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | SUBHADIP KOLEY | 4.2 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | SM/07317 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (115 out of 714), House Hold - 115 |  |  | VCH/002381/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | PRASANTA BHUIN | 8.81 | 0 | 0 | 0
Total | [13 empty] | 286.83 | 0 | 0