## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. |  | Junior Engineer | ORD/000193/2020-2021 | 210/BQA | 19/01/2021 | 18/02/2021 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | laying extra HDPE pipe line to cover Kamalpur Mantumura for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chinabari zone - H under Bankura sadar sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002949/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | M/S TARUN KUMAR PATRA | 4.8 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | laying extra HDPE pipe line to cover Kamalpur Mantumura for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chinabari zone - H under saltora - chhatna water supply scheme ( BRGF PH - I) Bankura sadar sub - Division of Bankura Division, PHE Dte. part - B |  |  | VCH/002950/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | M/S TARUN KUMAR PATRA | 4.78 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KALIPUR (Zone - C) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, No.of Mouza :- 06 nos, (Agaya , Pachasimul, Mechabaid , Banjurya, Haridi, Tentulberia) Total House Hold - 436 |  |  | VCH/002624/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | SWAPAN KUMAR UPADHYAY | 27.06 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukni Basa (91), Chholagara (96) & Dhadanga (97) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002627/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | TAPAS GHOSH | 12.24 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kadamberia (179) mouza by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household - 160 Nos. |  |  | VCH/002629/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | TAPAS GHOSH | 10.78 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. |  |  | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | SM/07319 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- Kamalpur (part), Total House Hold :-90 nos. |  | Junior Engineer | ORD/000227/2022-2023 | 248/KSD | 12/07/2022 | 27/07/2022 | M/S TARUN KUMAR PATRA | 3.87 | 0 | 0 | 0
Total | [13 empty] | 210.91 | 0 | 0