## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 2, ( (Subarda, Shalchura ) Total House Hold - 496 |  | Junior Engineer | ORD/000036/2020-2021 | 638/BQA | 10/02/2021 | 12/03/2021 | UNIVERSAL CONSTRUCTION | 37.1 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, ( Simla, Bank simul, Nekrakuada ) Total House Hold - 499 |  | Junior Engineer | ORD/000035/2020-2021 | 637/BQA | 10/02/2021 | 12/03/2021 | M/S TARUN KUMAR PATRA | 37.55 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Laying extra HDPE Pipe Line to Cover Simla, Bank simul mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. (Part- A) |  | Junior Engineer | ORD/000231/2021-2022 | 932/BSD | 04/10/2021 | 19/10/2021 | M/S TARUN KUMAR PATRA | 4.79 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Laying extra HDPE Pipe Line to Cover Simla, Bank simul mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. (Part- B) |  | Junior Engineer | ORD/000232/2021-2022 | 933/BSD | 04/10/2021 | 19/10/2021 | M/S TARUN KUMAR PATRA | 4.11 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Household survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR - Dhaban, Hapania, Jorehira, Kalipur, Tilna No. of Mouza :- 97 no. , Total House Hold - 15305 nos. |  |  | VCH/002965/2021-2022 | FHTC/26 | 25/03/2022 | 25/03/2022 | TECHVISION | 4.85 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Household survey of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR - Dhaban, Hapania, Jorehira, Kalipur, Tilna No. of Mouza :- 35 no. , Total House Hold - 3284 nos. |  |  | VCH/002966/2021-2022 | FHTC/26 | 25/03/2022 | 25/03/2022 | TECHVISION | 1.04 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. |  |  | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Makarkol (365) and Jukhanala (366) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 278 Nos.' |  |  | VCH/002692/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | SRIKANTA MONDAL | 10.55 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | SM/07322 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 02 nos, (Mouladanga & Mithila), Total House Hold - 519.. ( Sl .No.- 19) |  | Junior Engineer | ORD/000175/2020-2021 | 718/BQA | 19/02/2021 | 21/03/2021 | PARAMESWAR CHOWDHURY | 37.42 | 25.08 | 67.03 | 0
Total | [13 empty] | 211.08 | 25.08 | 11.88