## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, No.of Mouza :-3,(Nabanda, Kantapahari(Part) Haridi) Total House Hold - 402 |  | Junior Engineer | ORD/000037/2020-2021 | 639/BQA | 10/02/2021 | 12/03/2021 | SOUMITRA BHATTACHARYA | 33.83 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, No.of Mouza :-2,(Karkari, Kantapahari(Part) ) Total House Hold - 402 | Assistant Engineer | Junior Engineer | ORD/000038/2020-2021 | 640/BQA | 10/02/2021 | 12/03/2021 | M/S BIPUL BANERJEE | 33.79 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash (Zone - B) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur Name of OHR - Gumut No.of Mouza :- 02 nos, Beliara - 66, Dejjat - 66 Total House Hold - 977 |  |  | VCH/002688/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | PARAMESWAR CHOWDHURY | 60.61 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Laying extra HDPE pipeline to cover Rajsol (41) mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Hatikheda) Zone - I under Khatra Sub - Division of Bankura Division, PHE Dte. Block - Ranibandh , dist - Bankura part - B Sl no - 17 |  |  | VCH/002695/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | M/S TARUN KUMAR PATRA | 2.11 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Nabagram, No.of Mouza :-2,(Karkari, Kantapahari(Part) ) Total House Hold - 402 |  |  | VCH/000470/2022-2023 | FHTC/16 | 16/06/2022 | 16/06/2022 | M/S BIPUL BANERJEE | 25.53 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Naria (29) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002725/2021-2022 | FHTC/3 | 03/03/2022 | 03/03/2022 | UTTAM KUMAR SINHAMAHAPATRA | 0.45 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Makarkol (365) and Jukhanala (366) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 278 Nos.' |  |  | VCH/002692/2021-2022 | FHTC/2 | 02/03/2022 | 02/03/2022 | SRIKANTA MONDAL | 10.55 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | SM/07323 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (252) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002723/2021-2022 | FHTC/3 | 03/03/2022 | 03/03/2022 | UTTAM KUMAR SINHAMAHAPATRA | 0.51 | 0 | 0 | 0
Total | [13 empty] | 167.38 | 0 | 0