## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140 |  | Junior Engineer | ORD/000282/2020-2021 | 2083/BQA | 29/12/2020 | 28/01/2021 | GANGADHAR MONDAL | 9.79 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 03, Phulberia(PART-B) , Sirsa & Joykrishna pur Sarenga(PART-A), Total House Hold - 165 |  | Junior Engineer | ORD/000285/2020-2021 | 2086/BQA | 29/12/2020 | 28/01/2021 | M/S T.P. HAZRA & SONS | 11.55 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Joykrishna pur Sarenga(PART-B), Total House Hold - 176 |  | Junior Engineer | ORD/000286/2020-2021 | 2087/BQA | 29/12/2020 | 28/01/2021 | M/S SUPRIYA CHATTERJEE | 12.29 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 02 ( Bahadur pur , Oltara(PART-A), Total House Hold -141 |  | Junior Engineer | ORD/000281/2020-2021 | 2082/BQA | 29/12/2020 | 28/01/2021 | RUFIKUL MONDAL | 9.85 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 , Phulberia(PART-A) , Total House Hold - 150 |  | Junior Engineer | ORD/000284/2020-2021 | 2085/BQA | 29/12/2020 | 28/01/2021 | GANGADHAR MONDAL | 10.51 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000439/2020-2021 | 225/ BSD | 25/02/2021 | 12/03/2021 | RUFIKUL MONDAL | 4.78 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (FunctionalHouse Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - D ) & Saluka |  | Junior Engineer | ORD/000442/2020-2021 | 228/ BSD | 25/02/2021 | 12/03/2021 | M/S T.P. HAZRA & SONS | 2.72 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- (Ramchandra pur (Part - B ) |  | Junior Engineer | ORD/000440/2020-2021 | 226/ BSD | 25/02/2021 | 12/03/2021 | M/S SUPRIYA CHATTERJEE | 2.96 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- Ramchandra pur (Part - C ) |  | Junior Engineer | ORD/000441/2020-2021 | 227/ BSD | 25/02/2021 | 12/03/2021 | M/S T.P. HAZRA & SONS | 3.4 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 ( Ratganj Madhav pur ), Total House Hold -154 |  | Junior Engineer | ORD/000283/2020-2021 | 2084/BQA | 29/12/2020 | 28/01/2021 | RUFIKUL MONDAL | 10.79 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I), Name of mouza- Joykrishna pur Sarenga (PART- B), |  | Junior Engineer | ORD/000181/2021-2022 | 707/BSD | 17/06/2021 | 27/06/2021 | M/S SUPRIYA CHATTERJEE | 3.74 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I) Name of mouza - 03 nos, Phulberia (PART- B), Sirsa & Joykrishna pur Sarenga (PART- A) |  | Junior Engineer | ORD/000180/2021-2022 | 706/BSD | 17/06/2021 | 27/06/2021 | M/S T.P. HAZRA & SONS | 3.28 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | extra UPVC pipe line retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Sirsha Nutanpally to Palsona more under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Sirsha, Palsona. |  | Junior Engineer | ORD/000182/2021-2022 | 708/BSD | 17/06/2021 | 27/06/2021 | M/S T.P. HAZRA & SONS | 3.51 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 , Phulberia(PART-A) , Total House Hold - 150 |  |  | VCH/001597/2020-2021 |  | 15/03/2021 | 15/03/2021 | GANGADHAR MONDAL | 9.52 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 03, Phulberia(PART-B) , Sirsa & Joykrishna pur Sarenga(PART-A), Total House Hold - 165 |  |  | VCH/001591/2020-2021 |  | 15/03/2021 | 15/03/2021 | M/S T.P. HAZRA & SONS | 10.75 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of Mouza - PHULBERIA |  |  | VCH/000733/2021-2022 |  | 27/07/2021 | 27/07/2021 | GANGADHAR MONDAL | 3.15 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Extra UPVC pipeline of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura sadar Sub - Division under Bankura Division, PHE Dte. block - Barjora , name of OHR - Joykrisnapur (zone - l) name of mouza Oltara part - B sl no - 23 |  |  | VCH/001356/2021-2022 |  | 30/09/2021 | 30/09/2021 | GANGADHAR MONDAL | 4.52 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Joykrishna pur Sarenga(PART-B), Total House Hold - 176 |  |  | VCH/001590/2020-2021 |  | 15/03/2021 | 15/03/2021 | M/S SUPRIYA CHATTERJEE | 11.6 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Laying distribution system of UPVC pipe line with allied works from Near Beliatore police Station air valve to Oltora Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000328/2021-2022 | 758/ BSD | 26/07/2021 | 10/08/2021 | ZAKIR HOSSAIN MONDAL | 4.87 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | laying distribution system of UPVC pipe line with allied works from Oltotr to Madhavpur Village & Bahadur pur Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000329/2021-2022 | 759/ BSD | 26/07/2021 | 10/08/2021 | ZAKIR HOSSAIN MONDAL | 4.83 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) |  |  | VCH/002310/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | JAI BHARAT COMMERCIAL CORPORATION | 16.51 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- (Dadimukha, Saldanga), Total House Hold - 55 nos. |  |  | VCH/002807/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHENDU SEKHAR GORAI | 3.96 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | supplying laying fitting, fixing of HDPE pipe line at Kanchalla village & Samanta mara Adhibasi para under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000376/2022-2023 | 530/BSD | 28/07/2022 | 18/08/2022 | TARINI CHARAN UPADHYAY | 3.78 | 0 | 0 | 0
24 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & Jo | SM/07327 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 09 (Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalapahar, Kaljuri, Muraboni & Rasiknagar pur) Total House Hold - 932 ( Sl .No.- 21) |  | Junior Engineer | ORD/000178/2020-2021 | 720/BQA | 19/02/2021 | 21/03/2021 | M/S TARUN KUMAR PATRA | 96.69 | 13.42 | 13.88 | 0
Total | [13 empty] | 259.35 | 13.42 | 5.18