## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (PART-A) Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 1 no. i.e. Jamdoba-154, Habitation's Name:- Roypara, Kundupara, Palpara, Tantipara & Layekpara, Total House Hold - 72 |  | Junior Engineer | ORD/000101/2020-2021 | 161/VSD | 18/09/2020 | 09/10/2020 | MOHAN KUMAR ROY | 4.84 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 135 |  | Junior Engineer | ORD/000013/2020-2021 | 614/BQA | 10/02/2021 | 12/03/2021 | MOHAN KUMAR ROY | 9.86 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 3 nos. i.e. Jamdoba-154, Ichharia-155 and Bhabanipur- 165 , Habitation's Name : Jamdoba, Roypara, Tantipara, Ichharia, Dhallapara, Amchura, Kalaberia, Kalyanpur, Bhramanpara, Bhabanipur & Murhura. Total House Hold - 74. |  | Junior Engineer | ORD/000147/2020-2021 | 56/VSD | 10/02/2021 | 03/03/2021 | BIJOY KOLEY | 4.79 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 140 |  | Junior Engineer | ORD/000014/2020-2021 | 615/BQA | 10/02/2021 | 12/03/2021 | MOHAN KUMAR ROY | 9.87 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 65 |  | Junior Engineer | ORD/000141/2020-2021 | 22/VSD | 20/01/2021 | 19/02/2021 | MOHAN KUMAR ROY | 4.85 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 3 nos. i.e. Jamdoba-154, Ichharia-155 and Bhabanipur- 165 , Habitation's Name : Jamdoba, Roypara, Tantipara,Ichharia,Dhallapara,Amchura, Kalaberia, Kalyanpur,Bhramanpara,Bhabanipur & Murhura. Total House Hold - 162 | Assistant Engineer | Junior Engineer | ORD/000004/2021-2022 | 1506/BQA | 25/06/2021 | 25/07/2021 | MOHAN KUMAR ROY | 10.82 | 4.37 | 40.44 | 100
7 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, |  |  | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 65 |  |  | VCH/001584/2020-2021 |  | 15/03/2021 | 15/03/2021 | MOHAN KUMAR ROY | 4.73 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | FHTC Maintenance of Panchal Zone-I Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000299/2022-2023 | 317/VSD | 29/11/2022 | 14/12/2022 | SUBHENDU SEKHAR GORAI | 0.97 | 0.97 | 100 | 0
10 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Sinking of 1 no 300mm X 200mm X 240m deep Tubewell (Replacement Tubewell) at Ichharia (P.H No-2) by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe of Panchal Zone-I water supply scheme under Bishnupur Sub-Division of Bankura Division P.H.E Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000144/2023-2024 | 1329/BQA | 01/06/2023 | 01/04/2025 | M/S PARAMESWAR CHOWDHURY | 18.4 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | SM/07330 | Retrofitting | Additional Laying distribution system of Augmentation of Panchal Zone -I piped Water Supply Scheme within Sonamukhi Block under Bishnupur Sub - Division of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001365/2024-2025 | 3127/BQA | 19/12/2024 | 30/09/2026 | MUNSHI JAVEDUR JAMAN | 9.48 | 0 | 0 | 90
Total | [13 empty] | 128.87 | 5.34 | 4.15