## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Biradihi (39) & Diktor (40) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000113/2020-2021 | 171/BQA | 18/01/2021 | 17/02/2021 | PARTHA PRATIM CHATAIT | 26.52 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Biradihi (39) & Diktor (40) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) |  | Junior Engineer | ORD/000175/2021-2022 | 547/KSD | 29/06/2021 | 09/07/2021 | GANESH ROY | 2.91 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Biradihi (39) & Diktor (40) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 10) |  | Junior Engineer | ORD/000173/2021-2022 | 546/KSD | 29/06/2021 | 09/07/2021 | GANESH ROY | 3.27 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Work Order for Household survey in Biradihi (39), Diktor (40) & Bamni (42) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) |  | Junior Engineer | ORD/000514/2020-2021 | 312/KSD | 29/12/2020 | 28/02/2021 | GANESH ROY | 0.22 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Biradihi (39) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-C (Biradihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 19) |  | Junior Engineer | ORD/000696/2021-2022 | 80/KSD | 09/03/2022 | 19/03/2022 | PARTHA PRATIM CHHATAIT | 1.82 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000114/2020-2021 | 172/BQA | 18/02/2021 | 20/03/2021 | GANESH ROY | 18.65 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) |  |  | VCH/002321/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | PRADYUMNA KOLEY | 3.25 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  |  | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616 |  |  | VCH/002049/2021-2022 | FHTC/25 | 25/12/2021 | 25/12/2021 | UNICON INDIA | 75 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | laying extra HDPE pipe line to cover Diktor ( 40) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - C (biradihi) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - A |  |  | VCH/003006/2021-2022 | FHTC/26 | 26/03/2022 | 26/03/2022 | PARTHA PRATIM CHHATAIT | 4.72 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | laying extra HDPE pipe line to cover Diktor ( 40) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - C (biradihi) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B |  |  | VCH/003007/2021-2022 | FHTC/26 | 26/03/2022 | 26/03/2022 | PARTHA PRATIM CHHATAIT | 2.82 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | laying extra UPVC pipe line to cover chholagara ( 96 ) & Dhadanga (97) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - O (Madandihi) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B |  |  | VCH/003008/2021-2022 | FHTC/26 | 26/03/2022 | 26/03/2022 | TAPAS GHOSH | 4.97 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | "laying & repairing of UPVC pipe line (damaged due to widening - srenghening of Ranibandh to Barikul road ) at Haludkanali (102 ) mouzas of retrofitting Zone - P (Nachna) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, Jal Jeevan Mission (JJM) and JAL SWAPNA programme fund " |  |  | VCH/003009/2021-2022 | FHTC/26 | 26/03/2022 | 26/03/2022 | PRADYUMNA KOLEY | 0.61 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KENDBONI (Zone - P) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kendboni, No.of Mouza :- 08, ( Lapuria(PART), Dulal Kundi, Chharekha, Hatisal Pindri, Ladna, Garakusum, Mankanali & Khiraijuri), Total House Hold - 606" |  | Junior Engineer | ORD/000321/2020-2021 | 1370/BQA | 08/10/2020 | 07/11/2020 | SOUMITRA BHATTACHARYA | 41.63 | 2.75 | 6.61 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | supplying laying fitting fixing of HDPE pipe line from near Banogram village Burn Para to Malpara towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000515/2022-2023 | 505/BSD | 12/07/2022 | 01/08/2022 | BEAUTY CHATTERJEE | 4.98 | 4.98 | 100 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | SM/07336 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001547/2022-2023 | FHTC/06 | 06/01/2023 | 06/01/2023 | GANESH ROY | 6.02 | 0 | 0 | 0
Total | [13 empty] | 377.2 | 7.73 | 2.05