## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000116/2020-2021 | 174/BQA | 18/01/2021 | 17/02/2021 | DEBAKI RANJAN SARKAR | 30.83 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lachaipur (9), Fetapur (10), Gopalpur (11) & Tilabad (13) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000115/2020-2021 | 173/BQA | 18/01/2021 | 17/02/2021 | DEBAKI RANJAN SARKAR | 31.06 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Lachaipur (9) & Gopalpur (11) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 20) |  | Junior Engineer | ORD/000265/2021-2022 | 556/KSD | 29/06/2021 | 09/07/2021 | DEBAKI RANJAN SARKAR | 4.26 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 06, Patna Joykrishnapur, Kunjaban, Bhedua Purusottampur, Puramauna, Sankarpur & Narrah (PART), Total House Hold - 528.' |  |  | VCH/002878/2021-2022 |  | 16/03/2022 | 16/03/2022 | SWAPAN KUMAR CHANDRA | 9.23 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Laying of HDPE pipe line near Pakhanna village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  |  | VCH/002296/2021-2022 | FHTC/31 | 31/01/2022 | 31/01/2022 | GOPAL CHANDRA CHOWDHURY | 4.75 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Prakash, No. of Mouza :- 09 nos. i.e. Narayanpur-70, Uliara-71 & Tenera-80, Mahishkhoar-67, Ramnagar-68, Prakash-69, Katna-79, Basantapur-81 & Dihar-82, Total House Hold - 2326 |  |  | VCH/000204/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | SIB SANKAR CHOWDHURY | 85.33 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/003050/2021-2022 | FHTC/28 | 28/03/2022 | 28/03/2022 | DEBAKI RANJAN SARKAR | 0.84 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Work Order for Household survey in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 8) |  | Junior Engineer | ORD/000516/2020-2021 | 314/KSD | 29/12/2020 | 28/02/2021 | D. S. ENTERPRISE | 0.3 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 26/08/2022 | SUMITA UPADHYAY | 13.03 | 0.38 | 2.94 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kharkata, No. of Mouza :- 13 nos. i.e. Chanchar-144 Kadamdiha-145 Uparamdahara-146 Amdahara-147 , Choubeta-151, Kusumdiha-152 , Dhansole-153 , Phulboni-154, Hulmara-155 , Chackuporsole-160 , Asthasole-161 (Habitation's Name: ASTASOL, KURCHIDANGA), Sankarlayekerdanga- 162 & Jiabandi-163 [Adding DPR Sl. No -110 (Part), 111, 112, Total House Hold = [531 out of 921 +1284+1298] = 3113 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2020-2021 | 991/BQA | 26/02/2021 | 28/03/2021 | GOPAL CHANDRA CHOUDHURY | 234.49 | 100 | 42.64 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | SM/07338 | Retrofitting | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) |  | Junior Engineer | ORD/000085/2022-2023 | 323/KSD | 01/08/2022 | 16/08/2022 | PRADYUMNA KOLEY | 3.81 | 3.77 | 98.94 | 0
Total | [13 empty] | 417.92 | 104.15 | 24.92