## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 3 nos ( Susunia, Ethani, Tulsha (Part). ) Total House Hold - 552 | Assistant Engineer | Junior Engineer | ORD/000208/2020-2021 | 807/BQA | 23/02/2021 | 25/03/2021 | M/S BIPUL BANERJEE | 42.82 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  | Junior Engineer | ORD/000207/2020-2021 | 806/BQA | 23/02/2021 | 25/03/2021 | SOUMITRA BHATTACHARYA | 42.52 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 03 nos, ( Ampahari, Gopinathpur, Chakchaki,) Total House Hold - 518 |  |  | VCH/001489/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | SUMITA UPADHYAY | 32.36 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-01 no (Pinguri (Part-A ), Total House Hold -420 |  |  | VCH/001459/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | SUBHANKAR BANERJEE | 2.06 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Kusum Goria , Tajpur Rampur , Rajmadhavtir, Kotalpukur & Mahidara ), Total House Hold -963 |  |  | VCH/001750/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | GOPAL CHANDRA CHOUDHURY | 74.71 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 05 , Kolaberia (PART- A ) ,Bandarkhola, Ramharipur, Katapesia, Maitha Gopinathpur ), Total House Hold -426 |  |  | VCH/001513/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | UNIVERSAL CONSTRUCTION | 6.09 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sindurpeti (239), Tiring (244), Parashi Danga (247), Khayerbani (248) Bagakhulia (249) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001501/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | EARTH MOVING (INDIA) | 11.93 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Buriam (112) & Haludkanali (113) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 02 Nos. Total Household - 420 Nos. |  |  | VCH/001519/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | SUBHADIP KOLEY | 27.61 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | SM/07340 | Retrofitting | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Tilna (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Tilna (Zone - E), No. of Mouza :- 01 Ethani (Part), Total House Hold :- 17 nos. | Assistant Engineer | Junior Engineer | ORD/000140/2023-2024 | 101/KSD | 28/04/2023 | 28/05/2023 | TAPAS KUMBHAKAR | 0.95 | 0.93 | 98.66 | 100
Total | [13 empty] | 241.06 | 0.93 | 0.39