## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 05(Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurdanga), Total House Hold -451 ( Sl .No.- 14) |  | Junior Engineer | ORD/000167/2020-2021 | 713/BQA | 19/02/2021 | 21/03/2021 | SIB SANKAR CHOWDHURY | 41.68 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 02 ( Mathurberia,Rajmadhabpur), Total House Hold -138 ( Sl .No.- 16) |  | Junior Engineer | ORD/000170/2020-2021 | 715/BQA | 19/02/2021 | 21/03/2021 | I.R.CONSTRUCTION | 12.82 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 ( Srikrishnapur, Gangabundh, Saulia), Total House Hold -467 ( Sl .No.- 15) |  | Junior Engineer | ORD/000168/2020-2021 | 714/BQA | 19/02/2021 | 21/03/2021 | SIB SANKAR CHOWDHURY | 43.23 | 34.18 | 79.06 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Extra HDPE pipe line to cover Ganga Bandh mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000520/2021-2022 | 233/BSD | 15/03/2022 | 25/03/2022 | SIB SANKAR CHOWDHURY | 2.8 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Extra HDPE pipe line to cover Amtha mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000521/2021-2022 | 210/BSD | 11/03/2022 | 21/03/2022 | SIB SANKAR CHOWDHURY | 4.99 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. |  |  | VCH/002785/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 05 (Nabagram, Ailtha, Munipur, Bagneja & Upar bandh) Total House Hold - 605' |  |  | VCH/000217/2022-2023 | FHTC/08 | 08/04/2022 | 08/04/2022 | GOPAL CHANDRA CHOWDHURY | 6.47 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  |  | VCH/002587/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | M/S TARUN KUMAR PATRA | 179.79 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576' |  |  | VCH/000218/2022-2023 | FHTC/08 | 08/04/2022 | 08/04/2022 | GOPAL CHANDRA CHOWDHURY | 12.5 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 (Akurbad & Banki, ) Total House Hold - 633' |  |  | VCH/000216/2022-2023 | FHTC/08 | 08/04/2022 | 08/04/2022 | GOPAL CHANDRA CHOWDHURY | 8.22 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | SM/07346 | Retrofitting | Extra HDPE pipe line to cover Amtha mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 04 |  |  | VCH/001241/2022-2023 | FHTC/28 | 28/09/2022 | 28/09/2022 | SIB SANKAR CHOWDHURY | 4.94 | 0 | 0 | 0
Total | [13 empty] | 381.01 | 34.18 | 8.97