## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Dhobagram, Chila bakra, Na | SM/07347 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 09 Nos. ( Dhobagram, Chila bakra, Nayabadi, Sagunsora, Bhaluk geza, Shyampur, Khap, Shusunia & Dubraji) Total House Hold - 1055 |  | Junior Engineer | ORD/000041/2020-2021 | 643/BQA | 10/02/2021 | 27/11/2021 | GOPAL CHANDRA CHOUDHURY | 91.82 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Dhobagram, Chila bakra, Na | SM/07347 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Horoka (Zone - G) under Saltora-Block of Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 1 no, Gogra (Part) Total House Hold - 75 (Sl No of Work- 06) |  | Junior Engineer | ORD/000081/2020-2021 | 98/ BSD | 12/02/2021 | 04/03/2021 | MANAS DEY | 4.72 | 4.38 | 92.61 | 0
Total | [13 empty] | 96.54 | 4.38 | 4.53