## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha | SM/07349 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Chaturdihi. No.of Mouza :- 09 Nos. ( Bhagabanpur,Baindhka, Bhaturi, Jharia, Makarkendi, Rajkumar, Sibarampur, Dakhin bonkati & Kendhkun. ) Total House Hold - 1050 | Assistant Engineer | Junior Engineer | ORD/000408/2020-2021 | 403/BQA | 04/02/2021 | 21/11/2021 | GOPAL CHANDRA CHOUDHURY | 94.22 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha | SM/07349 | Retrofitting | Laying extra HDPE pipe line to cover Baindaka mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000561/2021-2022 | 835/BSD | 18/08/2021 | 02/09/2021 | GOPAL CHANDRA CHOWDHURY | 4.59 | 2.31 | 50.22 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha | SM/07349 | Retrofitting | Laying extra HDPE pipe line to cover Bhaturi mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000562/2021-2022 | 837/BSD | 18/08/2021 | 02/09/2021 | GOPAL CHANDRA CHOWDHURY | 4.82 | 4.22 | 87.5 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha | SM/07349 | Retrofitting | Laying extra HDPE pipe line to cover Bhagabanpur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chaturdihi (Zone- U) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000547/2020-2021 | 836/BSD | 18/08/2020 | 02/09/2020 | SUBHADIP KOLEY | 4.26 | 4.19 | 98.36 | 0
Total | [13 empty] | 107.9 | 10.72 | 9.94