## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) | SM/07350 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  | Junior Engineer | ORD/000066/2021-2022 | 2196/BQA | 25/08/2021 | 09/10/2021 | UNICON INDIA | 317.75 | 0 | 0 | 100
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) | SM/07350 | Retrofitting | Extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001011/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | MUNMUN UPADHYAY | 3.97 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) | SM/07350 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 03 nos, ( Ampahari, Gopinathpur, Chakchaki,) Total House Hold - 518 |  |  | VCH/001489/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | SUMITA UPADHYAY | 32.36 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) | SM/07350 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Kheyarkanali. No.of Mouza :- 01 nos, Khyerkanali (PART-1) Total House Hold - 145 |  |  | VCH/001514/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | PRADIP CHAKRABORTY | 11.26 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) | SM/07350 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :- 05 (Kusum Goria , Tajpur Rampur , Rajmadhavtir, Kotalpukur & Mahidara ), Total House Hold -963 |  |  | VCH/001750/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | GOPAL CHANDRA CHOUDHURY | 74.71 | 0 | 0 | 0
Total | [13 empty] | 440.05 | 0 | 0