## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Parkul (217), Mashara (218), Goaladanga (219), Chandanpur (261), Beniabaid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000087/2021-2022 | 2503/BQA | 23/09/2021 | 23/10/2021 | EARTH MOVING (INDIA) | 44.75 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Work Order for Household survey in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 26) |  | Junior Engineer | ORD/000529/2020-2021 | 327/KSD | 29/12/2020 | 28/02/2021 | TAPAS DEY | 0.26 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Work Order for Laying UPVC pipeline at Chandanpur village to increase pressure in Chandanpur (261) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-IIA (Baragari) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 26) |  | Junior Engineer | ORD/000658/2021-2022 | 87/KSD | 09/03/2022 | 19/03/2022 | BIKASH MANDAL | 3.04 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Laying HDPE pipeline to increase pressure to cover Mashara (218) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - IIA ( Baragari ) of Khatra - Hirbandh - Ranibandh W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission (JJM) and JAL SWAPNA under Khatra Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000759/2022-2023 | FHTC/01 | 01/08/2022 | 01/08/2022 | SUBHADIP KOLEY | 4.98 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Laying extra UPVC pipe lineto cover Beniabaid (262) & Kandrahara (263) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- IIA ( Baragari) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Khatra dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 10 part - A sl no -- 10 |  |  | VCH/002952/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | UNITED TRADERS | 4.44 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. |  |  | VCH/002888/2021-2022 |  | 16/03/2022 | 16/03/2022 | ALOK ENTERPRISE | 59.06 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Laying extra UPVC pipe lineto cover Beniabaid (262) & Kandrahara (263) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- IIA ( Baragari) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Khatra dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 10 part - B sl no - 11 |  |  | VCH/002953/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | UNITED TRADERS | 4.52 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Laying extra UPVC pipe lineto cover Parkul (217) & Goaladanga (219) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- IIA ( Baragari) of Khatra-Hirbandh-Ranibandh water supply scheme (BRGF ph - I project) block - Khatra dist - Bankura under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 14 |  |  | VCH/002951/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | UNITED TRADERS | 2.49 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Laying fitting fixing of HDPE pipe from Ghutgoria to Kulbona Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA) |  | Junior Engineer | ORD/000143/2022-2023 | 563/BSD | 29/07/2022 | 28/08/2022 | GOPAL CHANDRA CHOWDHURY | 4.99 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | SM/07353 | Retrofitting | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) |  |  | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 27/12/2022 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0 | 0
Total | [13 empty] | 325.58 | 0 | 0