## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baidyanathpur (118) mouza by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000075/2020-2021 | 481/BQA | 05/02/2021 | 07/03/2021 | APEX ENTERPRISE | 23.86 | 0.47 | 1.97 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Work Order for Household survey in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 16) |  | Junior Engineer | ORD/000359/2020-2021 | 45/KSD | 15/01/2021 | 15/03/2021 | TAPAS DEY | 0.3 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyambazar (109) Banbedia (111) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000077/2020-2021 | 483/BQA | 05/02/2021 | 07/03/2021 | GOUTAM BHATTACHRYYA | 20.37 | 2.37 | 11.64 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108) Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000076/2020-2021 | 482/BQA | 05/02/2021 | 07/03/2021 | GOUTAM BHATTACHRYYA | 16.61 | 1.14 | 6.89 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Laying extra upvc pipeline to cover Shyambazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme |  |  | VCH/001482/2021-2022 |  | 08/10/2021 | 08/10/2021 | BHATTACHARYYA ENTERPRISE | 4.86 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, |  |  | VCH/001560/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140, |  |  | VCH/001561/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | GANGADHAR MONDAL | 8.9 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Kadakuli roy para total House Hold - 75 Sl no - 02 , Tender No - 31/20-21/EE/BQA W/O NO- 551/BSD dt 13.11.2020 |  |  | VCH/000628/2021-2022 | FHTC/26 | 11/05/2021 | 11/05/2021 | SANJOY MONDAL | 4.55 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Laying extra UPVC pipe line to cover Shyam bazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme |  |  | VCH/001480/2021-2022 |  | 08/10/2021 | 08/10/2021 | APEX ENTERPRISE | 4.96 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Simulkundi (77) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) |  |  | VCH/002930/2021-2022 | FHTC/21 | 21/03/2022 | 21/03/2022 | SRIKANTA MONDAL | 1.97 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 |  | Junior Engineer | ORD/000017/2020-2021 | 619/BQA | 10/02/2021 | 12/03/2021 | MUNMUN UPADHYAY | 35.36 | 1.25 | 3.54 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | SM/07358 | Retrofitting | Laying HDPE pipeline from Sri Ramkrishna Shibananda Ashram road to Pitadungri village to increase pressure in Pitadungri (275) & Kuchiarmahar (276) Mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000056/2022-2023 | 1680/BQA | 27/07/2022 | 26/08/2022 | SUMITA UPADHYAY | 13.03 | 1.54 | 11.78 | 0
Total | [13 empty] | 185.04 | 6.77 | 3.66