## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 17/02/2021 | EARTHMOVING (INDIA) | 39.43 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000092/2020-2021 | 199/BQA | 18/01/2021 | 17/02/2021 | EARTHMOVING (INDIA) | 38.78 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Laying extra UPVC pipeline to cover Arkama (124) & Hazamdihi (233) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001317/2021-2022 |  | 28/09/2021 | 28/09/2021 | UNITED TRADERS | 4.76 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - barjora G.P chandar, Name of OHR - Lobason bauri para, chandar shib Total House Hold - 50 no - 03. |  |  | VCH/001256/2021-2022 | FHTC/02 | 02/08/2021 | 02/08/2021 | M/S PAUL BROTHERS | 4.27 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 21) |  |  | VCH/001328/2021-2022 |  | 28/09/2021 | 28/09/2021 | UNITED TRADERS | 4.87 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- (Ramchandra pur (Part - B ), |  |  | VCH/001587/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | M/S SUPRIYA CHATTERJEE | 2.76 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Laying extra UPVC pipe line to cover Naria (29), Benagaria (30), Hirakhon (31), mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/001232/2021-2022 | FHTC/13 | 13/08/2021 | 13/08/2021 | UTTAM KUMAR SINHAMAHAPATRA | 2.24 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Arkama (124) & Hazamdihi (233) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) |  |  | VCH/001329/2021-2022 |  | 28/09/2021 | 28/09/2021 | UNITED TRADERS | 4.12 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17), |  |  | VCH/001567/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | UNIVERSAL CONSTRUCTION | 37.69 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Laying extra UPVC pipeline to Cover Gaira, Arjunpur , Bahadurpur , Radhanagar, Moukura Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/001409/2021-2022 | FHTC/15 | 15/09/2021 | 15/09/2021 | SUBHADIP KOLEY | 3.8 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Work Order for Household survey in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 22) |  | Junior Engineer | ORD/000526/2020-2021 | 324/KSD | 29/12/2020 | 28/02/2021 | EARTH MOVING (INDIA) | 0.38 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001482/2022-2023 | FHTC/20 | 20/12/2022 | 20/12/2022 | MUNMUN UPADHYAY | 13.3 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Laying HDPE pipeline from Gadapathar College More to Nanda Primary School to increase pressure in Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001418/2022-2023 | FHTC/16 | 16/12/2022 | 16/12/2022 | DEBAKI RANJAN SARKAR | 19.69 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  |  | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 10/01/2023 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | SM/07359 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Singlahar (168), Paryasa (169), Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 4 Nos. Total Household - 589 Nos. |  | Junior Engineer | ORD/000031/2021-2022 | 1778/BQA | 09/07/2021 | 08/08/2021 | EARTH MOVING (INDIA) | 40.2 | 2.8 | 6.97 | 0
Total | [13 empty] | 250.87 | 2.8 | 1.12